## Sheet1
ARM Committee – Task Plan 2018-2023 |  |  |  | Session
Strategy Technical Domain | Task | Expected Output | WG | 8 | 9 | 10 | 11 | 12 | 13 | 14 |  | 16 | Status / %
|  | (Key: + planned work, x planned but no work carried out, > task extended, * task completed) | [8 empty] | 15
1. Standard 1010 – AtoN planning and service requirements
1.1. Obligations and regulatory compliance (RXXX) | 1.1.1. Develop guidance on regulatory/legal framework for Aton Authorities | a. New Recommendation and new Guideline; b. New Guideline(s) describing purpose, management, legislation needs, regulation needs, perhaps with examples of legislation and regulation clauses to assist understanding; c. Include guidance in terms of the requirement, composition and authority of a National Maritime Committee (ref MC L1.2 section 1d.3); d. Include guidance in terms of the content of a strategic plan for AtoN service delivery (ref MC L1.2 section 1d4) | 1 | [9 empty] | Cancelled following LAP advice | bar: Session 8 to Session 11
| 1.1.2. Revise G1054 Preparing for a Voluntary IMO Audit on Aids to Navigation Service Delivery (Nov 2006) | Revised Guideline to reflect change of IMO audit status – to include a checklist for IMSAS auditors regarding AtoN and VTS to fulfil PAP37 action. ARM11 - IMSAS Manual Updated and submitted to PAP/LAP. Revision of G1054 to commence at ARM12. | 1 | [9 empty] | Complete | bar: Session 10 to Session 14
1.2. Risk management (R1002) | 1.2.1. Review G1018 Risk Management to ensure compatability with risk toolbox. Includes full review of underlying Risk Toolbox documentation G1123, G1124, G1138 | Revised Guideline | 3 | [7 empty] | + | + | Complete | bar: Session 8 to Session 14
| 1.2.2. Review R0142 Maritime Data Sharing IALA Net to reflect new title “Maritime data sharing” and the storage and use of historical [AIS and other] data for risk analysis | Revised Recommendation - complete | 3 | [8 empty] | + | Ongoing | bar: Session 10; Session 12 to Session 14
| Consider need and drivers for data sharing, capture and analysis. | New Guideline incorporating a Conceptual framework for data sharing, capture and analysis | [8 empty] | +
| Identify possible tools for data capture and analysis. | Tools for data sharing, capture and analysis
Monitor development of framework and identified tools for data capture and analysis with IALA Secretariat.
| 1.2.3. Review G1086 Global Sharing of Maritime Data (June 2012) in collaboration with task 1.2.2 (R0142 review) | Revised Guideline | 3 | [7 empty] | + | + | Ongoing | bar: Session 9 to Session 10; Session 12 to Session 14
| 1.2.4. In cooperation with ENG (task 1.2.1) revise R0138 and G1058 and G1097 on simulation use by AtoN authorities | Revised Recommendation and Guideline to incorporate Korean input from ENG on AtoN simulator | 3 | [7 empty] | + | + | Complete | bar: Session 8 to Session 10; Session 12 to Session 14
| 1.2.5. Develop Recommendation for marine data sharing for risk assessment analysis or incorporate with R0142 task 1.2.2 | New Recommendation or extension of R0142
| 1.2.6. Develop guidance on cyber security for AtoN authorities in collaboration with all other Committees. Possibly complete at Cyber Security workshop. ARM11 - Input for the workshop to be forwarded. | New Recommendation and Guideline | 2 | [8 empty] | + | Ongoing | bar: Session 11 to Session 14
|  | Develop Basic Requirements and intersessional cross-committee gap analysis in Advance of Workshop | [8 empty] | +
| 1.2.7. Develop document to promulgate IALA risk management tool box to IMO (SN circular) | Input paper to IMO MSC with a revised IMO SN circular | 3 | [7 empty] | + | + | Will be progressed on completion of all other tasks. WP 23 -27 | bar: Session 13 to Session 14
1.3. Levels of service objectives (R0130) | 1.3.1. Deliberately blank
1.4. Quality management | 1.4.1. Revised Guideline G1052 Quality Management in [Marine] Aids to Navigation Service Delivery (Dec 2013), removing ISO copied text. | Revised Guideline | 1 | [7 empty] | + |  | Ongoing | bar: Session 10 to Session 14
1.5. AtoN planning | 1.5.1. Reformat and review the IALA MBS incorporating MAtoN. Needs General Assembly approval. | Revised MBS Recommendation and possible new Guideline including mobile AtoN, bearing in mind R1016 | 1 | [7 empty] | 0 |  | Complete | bar: Session 8 to Session 14
| 1.5.2. Assist ENAV with development of radio aspects of MAtoN and AMRD with IEC and ITU | Advice to ENAV for liaison notes to ITU and IEC and contribution to ENAV New Guideline on AMRD | 1 | [7 empty] | + | + | Complete | bar: Session 8 to Session 14
| 1.5.3. Undertake gap analysis of IALA guidance associated with the MBS, including 1078 The Use of AtoN in the Design of Fairways (June 2011), identify further work to add to the task plan at ARM8.Includes SIGNI buoyage and submerged breakwaters. | Revised Guidelines (TBA) - 1.5.3.1 - G1078 update to be complete at ARM14 | 1 | +++ | + | + | + | + | + | + |  |  | Complete
| 1.5.4. Develop guidance for navigators on the use of AtoN | New Guideline | 1 | [7 empty] | + | + | Ongoing | bar: Session 12 to Session 14
| 1.5.5. Review G1096 Anticipated User e-Navigation Requirements from Berth to Berth, for AtoN Authorities (May 2013) – may be deleted | Revised or deleted Guideline | 1 | [9 empty] | Completed and deleted | bar: Session 10 to Session 11
| 1.5.6. Develop guidance on AtoN provision in polar regions (winter conditions; possibly complete following liaison with ENG) | New Guideline and possible Recommendation. ARM11 - this has evolved into the practical aspects of AtoN provision in winter conditions and therefore passed to ENG - task complete. | 1 | [9 empty] | Task complete | bar: Session 10 to Session 14
| 1.5.7. Develop guidance on the provision of AtoN for autonomous vehicle/vessel operations (Maritime Autonomous Surface Ship, MASS) | New Guideline and possible Recommendation | 1 | [7 empty] | + | + | Ongoing. Working with ENAV. | bar: Session 14
| 1.5.8. Review and update Recommendation R-0139 on the Marking of Man-Made Offshore Structures to reflect trends in the proliferation of wind farms and other offshore platforms. | Revised Recommendation and possible new Guideline. ARM11 - task commenced. R0113 will be commenced at ARM14. | 1 | [9 empty] | Complete | bar: Session 10 to Session 14
| 1.5.8.1 Revise R0113 marking of Bridges to become a guideline positioned under R0139 |  | 1 | [9 empty] | Ongoing
| 1.5.9. Identify options for the future use of DGNSS stations in conjunction with ENG review of Recommendation R0150. | Draft update of Recommendation R0150 to ENG Committee. ARM11 - awaiting output from ENG. | 1 | [9 empty] | ENG completed this task | bar: Session 10 to Session 12
| 1.5.10. Develop Guideline on the Use of MAtoN | Guideline (New) in Advance of MBS review | 1 | [9 empty] | Task complete at ARM11 | bar: Session 8 to Session 10
1.6. Virtual marking | 1.6.1. Review R0143 Provision of virtual aids to navigation and G1081 Virtual AtoN to reflect developments | Revised Recommendation and Guideline | 1 | [9 empty] | 1081 Complete at ARM11. R0143 completed at ARM13 | bar: Session 8 to Session 13
2. Standard 1020 – AtoN design and delivery
2.1. Visual signalling | 2.1.1. In association with ENG review G1116 Selection of Rhythmic Characters and Synchronisation of Lights for [Marine] Aids to Navigation (Dec 2015) | Revised Guideline | 1 | [9 empty] | Task complete at ARM11 | bar: Session 8 to Session 9
2.2. Design, implementation and maintenance | 2.2.1. Review G1084 Procedure of the Authorisation of AIS AtoN | Revised Guideline | 2 | [9 empty] | On hold | bar: Session 10 to Session 11
| 2.2.1a Full review of A-126, G1084 and other AIS associated documentation | Consolidation of AIS related documentation | 2 & 1 | [7 empty] | + | + | Recommened to carryover into next work program | bar: Session 14
| 2.2.2. Provide guidance on the management of requirements and requirements traceability | New Guideline (Task Completed at ARM9) | 2 | [9 empty] | Complete | bar: Session 9 to Session 10
| 2.2.3 Test areas for autonomous vessels and vehicles | Marking of test area for autonomous and unmanned/remote controlled ships and vehicles, due to the fact that i.a. industry and scientific institutes in Sweden have made inquiries to the STA regarding such marking. | [8 empty] | + | + | Proposed by Sweden | bar: Session 14
| 2.2.4 Marking of ice roads | Marking of competition and event areas for activities such as swim runs, kayaking, rowing, sailing, racing boats, hovercraft, and boat exhibition etc. | [8 empty] | + | + | Proposed by Sweden | bar: Session 14
| 2.2.5 Competition and event areas | Marking of ice roads for vehicle traffic on lakes and archipelagos in the vicinity of fairways to prevent ice breaking of established ice roads. | [8 empty] | + | + | Proposed by Sweden | bar: Session 14
| Use of automatic alerts in relation to vessel traffic behaviour outside of VTS areas (electronic fence) | China MSA suggestion | [10 empty] | Proposed by China MSA
| Sustainability task to be identified | [11 empty] | Proposed by ENG
| Model course for Navigators on the use of Marine AtoN | [11 empty] | Proposed by SAMSA
3. Standard 1050 – Training and Certification
3.1. Training and certification | 3.1.1. Review G1020 Training Related to [Marine] Aids to Navigation (Dec 2005) | Revised Guideline in collaboration with WWA | 3 | [9 empty] | Complete | bar: Session 8 to Session 10; Session 12 to Session 14
3.2. Capacity building | 3.2.1. Review relevant sections of NAVGUIDE as requested by Secretariat | Revised NAVGUIDE section | All | [9 empty] | Ongoing | bar: Session 8 to Session 14
NAVGUIDE review to be led by IALA Secretariat
4. Standard 1060 – Digital Communication Technologies
4.1. Wide/Medium bandwidth systems (AIS & VDES) | 4.1.1. Review G1050 Management and Monitoring of AIS Information (Dec 2005) | Revised Guideline | 2 | [9 empty] | Closed - see 2.2.1a | bar: Session 9 to Session 11
Conduct Periodic Review (coordinate with WG3 (IALANET, etc.))
4.2. Harmonised maritime connectivity framework (CMDS) Maritime IoT ( Intelligent sensors, Aton monitoring) | 4.2.1. Maritime Connectivity | Define User Requirements for Maritime Connectivity | 2 | [9 empty] | On hold | bar: Session 9 to Session 10; Session 12 to Session 14
|  | Define User Requirements for the Maritime Internet of Things (Define Requirements for MRN Addressing) | 2 | [9 empty] | On hold | bar: Session 9 to Session 14
|  | Contribute to IALA submission to IMO | 2 | [9 empty] | Complete | bar: Session 8
5. Standard 1070 – Information services
5.1. Data models and data encoding (IVEF, S-100, S-200, ASM) | 5.1.1. Develop guidance on Maritime Services including the production of an 'e-Navigation Operational Service Description' | New Guideline on implementation of Maritime Services under IALA’s Remit to include development of MS17 & MS19 (provide Clarification of Digital Representations of Physical Service). Develop a description for MS17 and submit to IMO. | 2 | [7 empty] | + | + | Ongoing | bar: Session 9 to Session 14
| 5.1.2. New Guideline on Operational considerations for S-200 (S-201 AtoN information and S-230 Application Specific Messages) | Guideline on Operational considerations for S-200 | 2 | [7 empty] | + | + | Ongoing | bar: Session 9 to Session 14
| 5.1.3. Continue to Develop Product Specification S-201 in the Task Group already assigned | Product Specification S-201 Ed.1 | 2 | [9 empty] | Complete | bar: Session 9 to Session 11
| 5.1.4. Develop Annex C to S-201 | Develop Annex C to S-201 PS to Ed.1 ARM11 - Develop Guideline on the implementation of S-201 | 2 | [9 empty] | Ongoing / 70 | bar: Session 8 to Session 10
|  | Revise Annex C to S-201 PS to Ed.2. To incorporate S-100 ed.5 changes. | [8 empty] | + | + | bar: Session 11 to Session 14
| 5.1.5. Develop Requirements for S-125 | Draft Product Specification for S-125 to be delivered to IHO | 2 | [7 empty] | + | + | Ongoing / 25 | bar: Session 8 to Session 14
| 5.1.6. Coordination with IHO/WMO for S-100, S-200, and MRN management (S-100/S-200 message coordination with other Committees on S-2xx development) |  | 2 | [7 empty] | + | + | Ongoing | bar: Session 8 to Session 14
| 5.1.7. Develop guidance on MRN for users | Develop MRN User Guideline to Ed.1 | 2 | [9 empty] | Complete | bar: Session 8 to Session 10
|  | Review MRN User Guideline to Ed.2 | 2 | [9 empty] | Ongoing | bar: Session 11 to Session 14
| 5.1.8. Develop MRN Registry Submission & Maintenance Guideline for IALA Secretariat | MRN Registry Submission & Maintenance Guideline Ed.1 | 2 | [9 empty] | Complete | bar: Session 8 to Session 10
|  | MRN Registry Submission & Maintenance Guideline Ed.2 | 2 | [9 empty] | On hold | bar: Session 11 to Session 14
| 5.1.9. Develop Recommendation to cover MRN Guidelines | New Recommendation on MRN | 2 | [7 empty] | + |  | Complete | bar: Session 9 to Session 14
| 5.1.10. Coordinate Committee support for IALA representation at IHO working groups in cooperation with Secretariat (HSSC, S-100WG, NIPWG) | IHO coordination | 2 | [9 empty] | Ongoing | bar: Session 8 to Session 14
| 5.1.11. Monitor the development of S-201 Testbed | Update reports on S-201 testbed. NIPWIG attendance | 2 | [7 empty] | + | + | Ongoing / 75 | bar: Session 8 to Session 14
5.2. Data exchange systems (Traffic Information) | 5.2.1. Review G1105 SHORE‐SIDE PORTRAYAL ENSURING HARMONISATION WITH e‐NAVIGATION RELATED INFORMATION | Ongoing | 2 | [7 empty] | + | + | Ongoing | bar: Session 9 to Session 14
| 5.2.2. Develop Guideline on ship reporting from the shore‐side perspective | a. Ship Report Template Registry specifications and governance; b. Guideline on ship reporting tools; c. Minimum cyber security requirements for sharing ship report information; d. Guidance on migration from current ship reporting system to a harmonised and secure electronic system; e. Consider IEC (63173) route exchange work (S-421). | 2 | [9 empty] | Completed at ARM13 | bar: Session 9 to Session 13
| 5.2.2 develop Ed 2 Guideline G 1159 on ship reporting from the shore‐based perspective | [11 empty] | Proposal for WP 23 -27
5.3. Terminology, symbology, and portrayal | 5.3.1. Develop guidance on the symbology and portrayal of AtoN for charting | New recommendation and guideline that gives guidance on how to deal with new technology concerning symbology and IHO symbology catalogue. A gap analysis to be carried out. | 2 & 1 | [7 empty] | + | + | Joint IHO/IALA Workshop - September 22 | bar: Session 9 to Session 14
6. Other
6.1. Seminar | 6.1.1. Cooperate with WWA in providing Risk Seminar(s) |  | 3 | [7 empty] | + | + | Ongoing | bar: Session 8 to Session 14
6.2. Workshop | 6.2.1. Lead joint workshop with IHO on S-100/200 and portrayal workshop | New Guideline or content of other work streams. | 2 | [7 empty] | + | + | TBC | bar: Session 9; Session 14
| 6.2.2. Participate in ARM led joint workshop on cyber security | Guidance on cyber security | 2 | [7 empty] | + | + | Complete | bar: Session 9 to Session 14
| 6.2.3 Joint IMO IHO IALA Workshop regarding the management of S-100 PS in June 2020 (TBC) in Norway | Council approved. New Guideline or content of other work streams. | [10 empty] | September to 2022
AtoN Questionnaire |  | Review AtoN Questionaire - about to be published (Oct 19) | All | [9 empty] | Ongoing | bar: Session 9