# IALA VTS MANUAL - REVISED WORK PLAN – SEPTEMBER 2005

| Sect | Chapter No. | Title | Author | Initiate Drafting | Draft for Circulation to VTS Committee | Final version to Committee for agreement | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  | Foreword | Editor | VTS 22 | VTS 23 | DS | 1. This revised programme takes account of the changed Committee Meeting dates, shown below, and assumes the viability of the proposed drafting session in March 2006. 2. Committee approval will be required following completion of the work undertaken during the extra drafting session (DS). This will be done by an inter-sessional call for comments and/or agreement. |
|  |  | Preface | Editor | VTS 22 | VTS 23 | DS |  |
|  | 1 | Introduction Annex A: Definitions Annex B: Glossary of Abbreviations | Editor | VTS 20 VTS21 VTS21 | VTS 21 VTS21 VTS21 | VTS 21 VTS21 VTS21 |  |
|  | 2 | Legal Framework | Editor | VTS 21 | VTS 21 | VTS 22 |  |
|  | 3 | Regulation of VTS | Editor | VTS 21 | VTS21 | VTS 22 |  |
|  | 4 | Functions of VTS | WG1(+ 2/3) | VTS 20 | VTS 21 | VTS 23 |  |
|  | 5 | Types of VTS and Categories of Service | WG1 (+2/3) | VTS 21 | VTS 22 | VTS 23 |  |
|  | 6 | Principles of Traffic Management | WG1 | VTS 22 | VTS 23 | DS |  |
| 2 | 7 | Determining the need for a VTS | WG1 & 2 | VTS 20 | VTS 22 | VTS 23 |  |
|  | 8 | Planning and Organisation | WG 1 | VTS 20 | VTS 22 | DS |  |
|  | 9 | Procurement Considerations | WG2 | VTS 22 | VTS 23 | DS |  |
|  | 10 | VTS Equipment | WG2 | VTS 20 | VTS 23 | DS |  |
|  | 11 | VTS Personnel | WG3 | VTS 21 | VTS 22 | VTS 23 |  |
|  | 12 | Qualification and Training | WG3 | VTS 22 | VTS 23 | DS |  |
| 3 | 13 | VTS Information | Editor | VTS 22 | VTS 22 | VTS 23 |  |
|  | 14 | VTS Procedures - General | WG1 | DS | VTS 24 | VTS 25 |  |
|  | 15 | VTS Procedures - Emergencies | WG1 | DS | VTS 24 | VTS 25 |  |
|  | 16 | Administrative Requirements | WG3 (+2) | VTS 24 | VTS 25 |  |  |
|  | 17 | Archives and Records | WG2 (+1/3) | VTS 24 | VTS 25 |  |  |
|  | 18 | Public Information | WG3 | VTS 23 | DS | VTS24 |  |

VTS 21	 - Sep 2004		VTS 23	 - Sep 2005				VTS 24	 - Sep 2006		VTS 26	- Sep 2007

VTS 22	 - Mar 2005		Drafting Session(DS) - Mar 2006		VTS 25	 - Mar 2007

REVISION OF THE IALA VTS MANUAL - WORK TARGETS FOR VTS 23

The following stages are due to be progressed or completed (VTS23 in bold):

| Item (Lead author) (1) | Initiate Draft (2) | Circulate to VTS Committee for comment and agreement (3) | VTS Committee to approve final draft (4) |
| --- | --- | --- | --- |
| Foreword (Ed) | # VTS22 | # VTS23 | VTS24 |
| Preface (Ed) | VTS22 | VTS23 | VTS24 |
| Chapter 1 (Ed) Introduction Annex A: Definitions Annex B: Glossary of Abbreviations | Completed Completed Completed | Completed Completed Completed | ) Remains open for ) further additions ) arising from later ) chapters |
| Chapter 2 (Ed) Legal Framework | Completed | Completed | Completed |
| Chapter 3 (Ed) Regulation of VTS | Completed | Completed | Completed |
| Chapter 4 (WG1/2/3) Functions of VTS | Completed | Completed | Completed |
| Chapter 5 (WG1/2/3) Types of VTS and Categories of Service | Completed | Completed | VTS23 (Output Paper) |
| Chapter 6 (WG1) Principles of Traffic Management | Completed | VTS23 (Input Paper) | DS Mar 2006 (Output Paper) |
| Chapter 7 (WG1 &2) Determining the need for a VTS | Completed | Completed | VTS23 (Output paper) |
| Chapter 8 (WG1) Planning and Organisation | Completed | Completed | DS Mar 2006 (Output Paper) |
| Chapter 9 (WG2) Procurement Considerations | Completed | VTS23 (Input paper) | DS Mar 2006 (Output Paper) |
| Chapter 10 (WG2) VTS Equipment | Completed | VTS23 (input paper) | DS Mar 2006 (Output Paper) |
| Chapter 11 (WG3) VTS Personnel | Completed | Completed | VTS23 (Output paper) |
| Chapter 12 (WG3) Qualification & Training | # Completed | VTS23 (Input paper) | DS Mar 2006 (Output Paper) |
| Chapter 13 (Ed) VTS Information | Completed | Completed |  |
| Chapter 18 (WG3) Public Information | #### VTS 23 | DS Mar 2006 | VTS24 |

Notes on Drafting – see over

Notes on Drafting

Where the work on a chapter is identified in column 2 as ‘Initiate draft’, it is suggested that some or all of the following processes be used as a means of producing the initial chapter format and to provide a framework for further work and comment:

- Identify topic headings (VTS21/6/1, Annex A) as an initial template.  Expand these as necessary to provide a framework for drafting.

- Identify existing relevant material contained in the VTS Manual 2002. This may, in some cases, be a more appropriate starting point, for example, with Chapter 11, VTS Personnel. (Note: An electronic copy of the Manual (2002) is available.)

- Identify and include any additional relevant topic headings.

- Identify and include any additional relevant material from other sources.

- Identify paragraphs/sections that need original drafting.  Nominate author(s)

- Liaise with other WGs, as necessary, to determine the need to incorporate other material.

- Produce the above as a single draft chapter document as an output paper for the VTS Committee.

## Format

The provisional format for chapter layout is that used for Chapter 1, (and the drafts of Chapters 2 & 3) which has been approved by the VTS Committee. The format may require some modification later; when Chapters 1 to 6 (Section 1) are completed a review will be undertaken to ascertain whether further change is needed.

### Illustrations

Illustrations are very important to enhance the utility of the manual and relevant diagrams and photographs should be included in the appropriate parts of the text.  Clearly these need to be of a very high quality.  Where these are available they should be positioned where required, where material is not immediately available space should be marked in the text by the use of an empty text box.   Requests for illustrations/photographic material should be passed to the editor, who may be able to put authors in contact with possible sources.

IALA VTS MANUAL

CHAPTER STRUCTURE FOR 2008 EDITION

SECTION 1:	VTS - REGULATORY FRAMEWORK AND FUNCTIONS

Chapter 1 		Introduction

# Purpose of the Manual

IALA Publications

Organisation and Consultative Bodies concerned with VTS

Development of VTS - A Brief History

Annex A:   Definitions

Annex B:    Glossary of Abbreviations

Chapter 2		Legal Framework

International Law

IMO Conventions, Resolutions and Guidelines

National Law

`		Harbour/Port Byelaws and Regulations

Authority

Liability

Environmental Law

Chapter 3		Regulation of VTS

IMO resolution Guidelines for VTS

IALA

Other regimes - EU

National

The need for common approach to standards

Chapter 4 		The Functions of VTS

Safety of Maritime Traffic

Safety of Life

Risk Reduction

Risk Management

Protection of the Marine Infrastructure

Efficient Vessel Traffic Flow

Efficient management of Port marine resources

Protection of the Environment

Security in the Maritime Domain - Its impact on VTS

VTS in an inter-modal transport system

Search and Rescue

Chapter 5		Types of VTS  and Categories of Service - Requirements and

Considerations

Types of VTS:

Harbour and harbour approaches

Places of  Refuge (ports) – implications for VTS

Coastal waters and International Straits

Waterways governed by Treaty

Waterways not governed by Treaty

Places of Refuge (non port) – implications for VTS

Offshore

Legal status

Inland Waterways

Categories of Service:

Information Service

Navigational Assistance Service

Traffic Organisation Service

Allied Services

Chapter 6		Principles of Traffic Management

Development of safe standard operating procedures

Principles of safe waterspace and traffic management

Two-way and one-way traffic occupancy; channel width, length, points-of-no-return, ship size and manœuvrability.

High-risk ships and cargoes

Risk induced by geography and hydrography

Other factors that can increase risk.

Allocation of waterspace. Slot management

Authorisation of ship movements, allocation of priority

Provision of navigation assistance

Traffic organisation service

Shore based Pilotage

SECTION 2		ESTABLISHING AND STAFFING A VTS

Chapter 7		Determining the Need for a VTS

Needs Analysis, including those of allied services

Hazard Identification

Risk assessment

Risk Control Options

Service provision

Cost/benefit Analysis

International Regulations

Chapter 8 		Planning and Organisation of VTS

Geography/Hydrography

Area limits, boundaries, Sectors, Coverage

Positional and Navigational Accuracy requirements.  Chart Accuracy.

Services

Service provision: mandatory/voluntary

Categories provided

Allied Services, including SAR

Management

Prohibited or Dangerous areas, safety zones (place of safety), anchorages

Traffic management, TSS, Separation Criteria

Pollution Control

Surveillance and Monitoring

VTS Personnel

Pilot/VTS interface.  The role of Pilots in a VTS

Legal  Basis

Constitution

Enforcement, Control, Direction (definitions/Difference)

Infringement of Regulations.

Contributory and Participatory Navigation Assistance

Advice and Information Services

Accident avoidance.

Chapter 9 		Procurement Considerations

Procurement Process:

Requirements capture

Feasibility studies and project definition

Options

Development, manufacture, installation and acceptance.

Demonstrators and modelling.

Project Management:

Management plan

Quality

Project risk plan

Scheduling

Acceptance testing

International Standards

Human factors

Chapter 10		VTS - Equipment

Introduction

Performance Requirements

Non-functional Requirements

Sensors

Radars

AIS/Transponders

Communications DF

Optical, TI, LL devices

Meteorological data

Tide, Tidal & Wave  Data

Communications

Voice HF/UHF/VHF/SHF

Data

EDI/e-mail

Telephone/Fax/Telex

Traffic Lights

Processing

Data Displays; Symbology

Correlation/ Fusion

Sensor Co-ordination 	Track combining

Track Table

Traffic Image

Tidal stream model and display

Depth of water/ height of tide model

Dynamic safe-depth (UKC) model

Alarms

Presentation

Displays, HMI, Symbology, Audio

Pilot aids - carryaboard equipment

Information Management

Database management systems

Standards, Accuracy, Quality.

Work Environment

Air supply

Lighting

Workstations

Equipment spaces

Fire/lightning protection

EMC

Security

Chapter 11 		VTS Personnel

Key personnel - ashore and afloat

The Ships Captain

Pilot

VTS

Captain/Pilot/VTS relationship

VTS Manager

VTS Superviser/Watch leader

VTS Operator

VTS Centre - watch organisation

Functions, duties & tasks

Delegated responsibilities.

Chapter 12		Qualification and Training of VTS Personnel

International Framework - STCW

Recruitment, Training and Certification

Model Courses

Refresher training and validation.

SECTION 3  		CONDUCT AND MANAGEMENT OF VTS OPERATIONS

Chapter 13		VTS Information and its Promulgation

This chapter provides a template from which VTS authorities could construct their own data sheets of information needed in the VTS centre and made available on the web and in appropriate nautical publications.  Methods of Promulgation.

Chapter 14		VTS Procedures

Data acquisition, reports, reporting points.

Identification.

Development of Traffic image

Traffic organisation and management.

Monitoring and authorising traffic movements

Passage Plans; exchange electronically

Detection of unsafe/unauthorised operations:

Infringements of exclusion zones

Infringements of separation intervals

Provision of support services

Relationships with Pilots and Ship's Masters

Chapter 15		VTS Procedures - Emergencies

Roles, responsibilities, pre-planned responses and co-ordination with other agencies in the general event of accident/emergency and specifically including:

Collision

Stranding

Fire on-board

SAR

Oil spill

Sinking

Hazardous cargo incidents

Terrorist action

Procedures for dealing with a disaster (eg fire) or malfunction of the VTS and its equipment

Chapter 16		Administrative Requirements for Operating a VTS

Co-ordination and planning of local resources.

Liaison with allied services

Agents

Customs

Security agencies

Quarantine

Auto-billing

PEC

Chapter 17		Archives and Records

Required to assist:

Re-construction of marine incidents

Litigation

Administration (Chapter 16)

Shipping , masters, pec data.

Chapter 18		Public Information

Public awareness, development of public image of VTS

Routine dealings with press and media.

Procedures for handling media following accidents and emergencies.