# Work Programme for completing the revised/new resolution for VTS.

| **Task** | **2018** | | | | **2019** | | | | | | | |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **IM[[1]](#footnote-1)**  **(10-13 Apr 2018)** | **ICG[[2]](#footnote-2)** | **VTS45**  **(1-5 Oct 2018)** | **ICG** | **NCSR 6**  **(16-25 Jan)** | **VTS46**  **(25 Feb – 1 Mar 2019)** | **ICG** | **Workshop**  **(13-17 May 2019)** | **MSC101**  **(5-14 Jun 2019)** | **ICG** | **VTS47**  **(23-27 Sep 2019)** | **NCSR 7**  **(Jan/Feb 2020)** |
| IALA intersessional meeting to establishing a common understanding of the submission and the tasks required | X |  |  |  |  |  |  |  |  |  |  |  |
| Draft skeleton for revised/new Resolution |  | X | X |  |  |  |  |  |  |  |  |  |
| Draft Work Plan |  | X | X |  |  |  |  |  |  |  |  |  |
| Prepare proposal for a Workshop on the revision of A.857(20) for Council approval |  | X | X |  |  |  |  |  |  |  |  |  |
| **First draft** of revised/new Resolution |  |  | X |  |  |  |  |  |  |  |  |  |
| Information Paper/s to NCSR and MSC[[3]](#footnote-3)   * Status of the revision * Invitation to the workshop |  |  | X | X | X |  |  |  | X |  |  |  |
| **Second draft** of revised/new Resolution |  |  |  | X |  | X |  |  |  |  |  |  |
| **Workshop** with stakeholders to review the draft revision |  |  |  |  |  |  |  | X |  |  |  |  |
| **Final draft** of revised/new Resolution |  |  |  |  |  |  | X |  |  | X | X |  |
| Review by NCSR of final revised/new Resolution for approval by the Committee and subsequent adoption by the Assembly |  |  |  |  |  |  |  |  |  |  |  | X |

1. IALA Intersessional Meeting of Working Group 1 of the VTS Committee [↑](#footnote-ref-1)
2. IALA Correspondence Group (ICG) for the revision of A.857(20) [↑](#footnote-ref-2)
3. Note submission end dates and need for Council approval:

   NCSR6 - submission deadline is 16 Oct. 2018

   MSC101 - submission deadline is 02 Apr 2019 (non-bulky documents)

   NCSR7 - submission deadline will be XX Oct 2019 [↑](#footnote-ref-3)