# STATUS OF THE NAVGUIDE

# ANM5 – WG2

All the sections of the NAVGUIDE were combined into a single master file. This file is: ANM5_WG2_output_navguide.doc. John Arenstam (USCG) is in charge of the consolidation of the Master File.

| Section | Action completed at ANM5 | Action required |
| --- | --- | --- |
| Forward | - None | - It is proposed that both the Secretary General and the President of IALA produce and sign the Forward - The secretariat is requested to bring this action item to the Sec. Gen. and to the President - To be finalized by January 31, 2005 and sent to J. Arenstam (US) for inclusion in the NAVGUIDE master file - To be revised at the final revision at ANM6 |
| Preface | - The revision was completed at ANM4 | - To be revised at the final revision at ANM6 |
| Chapter 1 - IALA | - A proposed Table of contents was prepared at ANM5 (ref:ANM5_WG2_output-Chapter 1_toc.doc). | - It is requested that the IALA Secretariat prepare Chapter 1 by January 31, 2005 based on the proposed table of contents. - To be finalized by January 31, 2005 and sent to J. Arenstam (US) for inclusion in the NAVGUIDE master file - To be revised at the final revision at ANM6 |
| Chapter 2 – Concepts and accuracy of navigation | - The revision was completed at ANM5 | - To be revised at the final revision at ANM6 |
| Chapter 3 – Aids to Navigation | - The revision was completed at ANM5 | - To be revised at the final revision at ANM6 |
| Chapter 4 – Other facilities | - The revision was completed at ANM5 | - To be revised at the final revision at ANM6 |
| Chapter 5 – Power Supplies | - The revision was completed at ANM5 | - To be revised at the final revision at ANM6 |
| Chapter 6 – Management Issues | - All inputs were combined into a new version of Chapter 6. - Juan Rebollo prepared a new version of the following: - 6.1.7.1 (Product Quality) - 6.1.7.2 (Service Quality) | - There are still missing input for 4 sections: - Gary Prosser (Australia) should complete the revision of section 6.1.3 (Risk Management) by January 31, 2005. - Raul Escalante will adapt the following sections from Pedro Rodriguez (Venezuela) in time for submission on January 31, 2005. - 6.1.7.7 (ISO 19011- Env. Quality) - 6.3.1.2 (Labor & Health) - EEP needs to review the section 6.2 (environment). In order to have this section in time for January 31, 2005, it is asked to the secretariat to contact the chairman of EEP and ask for the submission of a revised section 6.2. - These inputs, including the section 6.2 from EEP, need to be to be finalized by January 31, 2005 and be sent to J. Arenstam (USCG) for inclusion in the NAVGUIDE master file. |

ANM5-WG2-output-Status-navguide.doc