Report of the 5th Session of the IALA EEP Committee
Oct. 4-8, 2004

Executive Summary:

Annex 6, Action items 2, 3, 5, 6, 8, 13, 16 and 18 and Annex 7, amended work programme, are brought to the attention to Council

The EEP Committee met in Dublin, Ireland, immediately following the IALABATT/IALALITE Workshop.  The committee continued work according to their revised, detailed, work programme.  The combination of delayed items, items identified for completion at EEP5 and items completed early led to a significant number of completed items this session.

The Committee prepared the following documents for review by the Council:

- Draft IALA Guidelines on Environmental Considerations In AtoN Engineering (completed 2 sessions early) – To Approve  (Council Agenda item 6.5.3 refers)

- Draft Revision to IALA Guidelines on Availability And Reliability (delayed 1 session) - Theory And Examples – To Approve  (Council Agenda item 6.5.2 refers)

- Draft IALA Guidelines On Data Collection for AtoN Performance Calculation – To Approve  (Council Agenda item 6.5.4 refers)

- Draft Guidelines for the Ambient Light Levels at which AtoN Lights Should Switch On And Off – To Approve  (Council Agenda item 6.5.5 refers)

- Draft Guidelines on Solar Sizing (delayed 1 session) – To Approve  (Council Agenda item 6.5.6 refers)

- Draft Guidelines on Maintenance of Small Buoys and Small AtoN Structures (completed 1 session early) – To approve  (Council Agenda item 6.5.7 refers)

- Draft IALA Guidelines Sector Lights (completed 1 session early) – To Approve  (Council Agenda item 6.5.8 refers)

The Committee also noted the recently approved IALA Guidelines on the Certification of Marine Aids to Navigation Products.  Despite a detailed study of the text it was, however, not completely clear to the Committee how the Certification Templates are to be used in each of the 3 different processes outlined in the Guidelines.  The Committee therefore requests that the Secretariat provide clarification on this item (action item 11 refers).  Also, the Committee requests that the text of the IALA Guidelines on the Certification of Marine Aids to Navigation Products be amended to better explain the use of the Certification Templates in conjunction with each of the 3 different procedures.

The Committee noted that monitoring of Task M2 – Monitor developments in AtoN support structures and other equipment - has indicated developments in synthetic moorings which requires close review and possible revision of existing documentation.  They ask that the Council approve the promotion of this Monitoring Item to a Work Item.

The Committee also reviewed the recommendations from the IALABATT/IALALITE Workshop and noted that some of these are compatible with their existing workprogramme.  An Ad Hoc Group to work to review all aspects of light to update the existing documentation and include recent developments was proposed (EEP5/output/15).  The Council is asked to approve the formation of such a group.

Table of Contents

1	General	3

2	Review of Action Items	4

3	Review of Input papers	4

4	Reports from other bodies	4

5	Report from Rapporteurs	5

6	Work Programme	6

7	Report from WG1 – Fixed and Floating Support Structures and Power Systems	6

8	Report from WG2 – QA, Availability and Certification	8

9	Report from WG 3 – Environment and Publications	10

10	Report from WG4 – Light and Colour	10

11	Report from WG 5 - Preservation of Historic Lighthouses	12

12	Any Other Business	14

Annex 1 - IALA Committee Agenda EEP5	16

Annex 2 – EEP5 Participants	18

Annex 3 – Working Group Participants	22

Annex 4 – List of Input papers Session 5, Oct. 4-8, 2004	25

Annex 5 – List of Output and Working Papers	31

Annex 6 -  Action Items	33

Annex 7 – Detailed Work programme	37

Annex 8 - IALA Committee Provisional Agenda EEP6	55

Annex 9 – Developments in Lighthouse Preservation / Technical Visit Information	57

| EEP Committee 5th Session | EEP5/output/16 Oct. 8, 2004 |
| --- | --- |

Report of the 5th Session of the IALA EEP Committee

# General

The 5th meeting of the EEP Committee was held from Oct. 4-8, 2004 at Clontarf Castle, Dublin, Ireland with O. Eriksson as Chair and S. Doyle as Vice-Chair.  The secretary for the meeting was J. Carson-Jackson.

Apologies were received from:

| COOPOO, Kiru | NPA SA | South Africa |
| --- | --- | --- |
| LEA, Roger | Dow Corning | UK |
| MONRAD-KROHN, Danckert | Vest-Agder County Council | Norway |

The Chairman opened the meeting and welcomed all members, with a special welcome for new members.  He thanked the Commissioners of Irish Lights for hosting the EEP5 meeting, especially Pauline MacMahon and Fiona Lee who will be providing secretarial support.  He then welcomed all participants to Dublin.  The Chairman noted the apologies for absence.

Jillian Carson-Jackson presented the apologies of the Secretary General, as he was unable to attend the opening of the meeting.  She then introduced a video presentation from Mr. Clive Davidson, AMSA, President of IALA.  This video is a result of the ongoing work on a promotional video for IALA, however it is a separate video that has been produced specifically for presentation to the IALA Committees.

S. Doyle of CIL provided a briefing on administrative details, including a safety briefing.

The Chairman then began the review of the Agenda, noting the work that was done intersessionally to move various documents forward, thanking members for their input to EEP5.

## Annexes

### Agenda

The agenda was reviewed and adopted.

A copy of the agenda is provided in Annex 1.

### Participants

A list of participants is provided in Annex 2.

### Working Group Participants

A list of working group participants in provided in Annex 3.

### Input Papers

A list of input papers is provided in Annex 4.

### Output and Working papers

A list of output and working papers is provided in Annex 5.

### Action Items

A list of action items is provided in Annex 6.

### Work Programme

A Revised Work Programme is provided in Annex 7.

### Provisional Agenda EEP6

A provisional agenda for EEP6 is provided in Annex 8.

### Developments in Lighthouse Preservation

The reports from members on the status of lighthouse preservation is included at annex 9.

# Review of Action Items

Input paper EEP5/2/1 refers.

The Action Items from EEP4 were reviewed and noted as complete with the following exceptions:

## Action Items for the Secretariat

26 – The Secretariat was asked, when priorities allow, to install the necessary template for the IALA web site portal relating to historic lighthouses for public relations purposes.   An update on this was provided during EEP5.

5 – The Secretariat was asked to forward the discussion paper on PHL/EEP Merger Evaulation (EEP4/WG5/WP1) to EEP5.  This document was brought forward during the meeting for review by EEP5 WG5 members.

## Action Items for EEP Members

WG Chairmen were asked to review specific action items for EEP Members during their opening sessions.  Specific reference to action items for EEP Members are identified in WG reports.

# Review of Input papers

A detailed review of EEP5/3/1 – Input Papers - was carried out.  Papers were referred to Working Groups as indicated in Annex 4.

# Reports from other bodies

Report EEP5/4/1 – EEP5/4/5 and EEP5/4/info1 refers.

The reports from other bodies were noted.

## Report from IALA Council

The Report from IALA Council Session 34 was noted.  The items of specific relevance to the Committee were highlighted.

### IALA Certification Process

The IALA Guidelines on Certification were approved at Council Session 33.  It was noted at this time that there would be a requirement for development of Product Certification Templates.  This item was addressed in working group 2. (Section 8.4 refers)

### IALA Risk Assessment Tool

The Committee noted with interest the completion of the Risk Assessment tool, as well as the training workshop planned for Montreal, Canada, Nov. 8-10, 2004.

Action Item

The Secretariat was asked to provide information to EEP Members on or before EEP6 on the process for obtaining copies of the IALA Risk Assessment Tool.

## Report from MSC78

The report from MSC78 was noted.

## Report from IMO NAV50

The report from IMO NAV50 was noted.

## IALA Submission to NAV50 – IALA Risk Assessment Tool

The submission was noted. (Section 4.1 refers)

## Report from Working Group on Aids to Navigation Information Service (ANIS)

The report from the ANIS Working Group was noted.

## Draft Report from IALABATT/IALALITE5 (info document)

The Draft Report was noted and items of particular interest to the EEP Committee were highlighted.  The Conclusions and Recommendations from the workshop were reviewed and actions assigned as appropriate.  It was stressed that this was a draft report of the workshop.

# Report from Rapporteurs

Monitoring items were reported through a verbal process.

## Development of computer methods and applications to simplify design and management of AtoN (M1);

This item is being dealt with through a questionnaire on Computer Methods and Applications.  (Section 9.3 refers)

## Developments in AtoN (M2);

There were no specific developments in AtoN to report at this time.  Discussion on synthetic moorings indicated a strong interest in developments in this area.  It was decided that there may be benefit in reviewing the existing Guidelines on Synthetic moorings.  Some members noted that this should be done in the very near future, as there is some urgency in the matter.

It was also noted that developments in self-contained lanterns were providing a significant change to the AtoN services, and that it would be valuable to look at buoy and mooring options, perhaps with a view to a complete buoy and mooring package that was linked to the lantern developments.  Specific areas to be reviewed would include: Materials to be used; Assembly of units; and Retrieval from different platforms (i.e. buoy vessel, contractor, etc.)

Action Item

The Secretariat was asked to highlight the concerns of the committee to the Council with regards to developments in synthetic moorings, including the possibility to review and amend the existing guideline on synthetic moorings in the near future.

The Secretariat was asked to bring the review of existing guidelines on synthetic moorings to Council as an additional work item as per IALA Rules of Procedure.

## International progress on colours of light signals, calculations of the effective intensity of flashing lights and determination of luminous intensity (M3);

It was noted that these developments were discussed at length during the IALABATT/IALALITE 5 Workshop and that the Draft Report provides a basis for further work requirements.  Of particular interest is the need for further work in the development of light measurement. (Section 4.6 refers)

## Monitor Developments in Renewable Energy Sources(M4)

It was noted these developments were discussed at length during the IALABATT/IALALITE 5 Workshop and that the Draft Report provides a basis for further work requirements.

# Work Programme

Five working groups were established.

| Working Group | Working Group Chair |
| --- | --- |
| WG1 – Fixed and Floating Support Structures and Power Systems | Adrian Wilkins |
| WG2 – QA, Availability and Certification | Clive Baker |
| WG3 – Environment and Publications | Roger Beauchesne |
| WG4 – Light and Colour | Seamus Doyle |
| WG5 – Preservation of Historic Lighthouses | Larry Wilson |

# Report from WG1 – Fixed and Floating Support Structures and Power Systems

WG1 was tasked to respond to input papers EEP5/6b/1, EEP5/6c/1, EEP5/6d/1, EEP5/6d/2, EEP5/6d/3, EEP5/6e/1, and EEP5/8/1.

Action items from EEP4 were reviewed by WG1.

## Develop Guidelines on Maintenance Practices for AtoN (Item 1.1; Task 2)

The WG reviewed the input document, “Draft Guidelines on Maintenance of Buoys and Small ATON Structures” (EEP5/output/11), and incorporated considerable input from the WG members.  The draft Guidelines were reviewed and approved by the EEP Committee for forwarding to Council.

Action Item

The Secretariat was asked to forward the Draft Guidelines on Maintenance of Buoys and Small ATON Structures” (EEP5/output/11)to Council for approval.

## Revise Guidelines on Battery Handling and Maintenance (Item 1.5; Task 15)

The WG reviewed the input document, “Draft Guidelines on Secondary Batteries for Aids to Navigation” (EEP5/6c/1).  This input document represented a complete reformatted version of the draft Guidelines on Battery Handling and Maintenance, and was prepared intersessionally as an action item from EEP4.  The content of the document was approved by the WG in its present form, however two new battery types identified at IALABATT/IALALITE require specialist input.  G. Cunty and M. Waddell agreed to undertake the review work intersessionally.  The intent of the WG is to have a finalized document available for EEP member review prior to EEP6.

Action Items

G. Cunty and M. Wadell were asked to modify the Draft Guidelines on Battery Handling and Maintenance (EEP5/6c/1)  to incorporate the information on the new battery technology identified at IALABATT/IALALITE 5, and forward the modified document to the WG1 Chairman by 10 Dec 04.

The Chairman, WG1, A. Wilkins was asked to finalize the Draft Guidelines on Battery Handling and Maintenance (EEP5/6c/1) as received from G. Cunty and M. Wadell  and forward it to the Secretariat for posting on the EEP Committee web site by 1 Jan 05.

The Secretariat was asked to post the Draft Guidelines on Battery Handling and Maintenance (EEP5/6c/1) as revised, to the Committee Web site by 15 Jan. 05.

The EEP members are asked to review the Draft Guidelines on Battery Handling and Maintenance (EEP5/6c/1) as revised, and provide comments to A. Wilkins by 1 Apr 05.

## Provide Guidance on an IALA Solar Design program (Item 1.6; Task 16)

The WG reviewed the input document “IALA Solar Sizing Program” (EEP5/6d/1) and the comments on solar sizing from Spain (EEP5/6d/3).  The WG agreed that this work item is now complete.  After discussing the end user agreement prepared by the Secretariat (EEP5/6d/2), the program authors (Germany) were satisfied that the program (with the user agreement) is now ready for publication.  The final document (EEP5/output/10) was reviewed and approved by the EEP Committee for forwarding to Council.

Action Item

The Secretariat was asked to forward the draft IALA Guideline on Solar Sizing (EEP5/output/10) to Council for approval.

## Prepare guidelines on the methodology for cost/benefit analysis of different types of buoys (Item 1.8.8)

The WG reviewed the input document “A Methodology for Cost Benefit Analysis of Buoys” (EEP5/6e/1).  Since this item relates to comparing different types of buoys, the WG decided that it would be appropriate to combine this task with the work on input paper EEP5/8/1 (large plastic buoys).  After extensive discussion, the WG considered that it would be practical to work on this issue intersessionally.  The intent is to build on the material contained in the two input papers and develop a methodology for performing life cycle cost comparisons of different buoy types (e.g., steel versus plastic).  The WG anticipates having a draft document available for EEP member review prior to EEP6.

Action Items

A. Wilkins and W. Danzik were asked to lead the intersessional effort to develop a draft methodology guideline for cost/benefit analysis of different types of buoys, with input from other interested WG members.  A draft document will be provided to the Secretariat for posting on the EEP Committee web site by 1 Apr 05.

EEP members were asked to review the draft methodology guideline for cost/benefit analysis of different types of buoys and bring any comments to EEP6.

# Report from WG2 – QA, Availability and Certification

The Working Group was asked to respond to input papers EEP5/6f/1, EEP5/6f/2, EEP5/6f/info 1, EEP5/6f/info 2, EEP5/6g/1, EEP5/6h/1, EEP5/6h/info 1, EEP5/6h/2, EEP5/6h/3, EEP5/6h/4, EEP5/6h/5.

Action items resulting from EEP4 were reviewed.

## Revise Guidelines on the Quality Assurance, Availability of Systems and Components (Item 2.1; Task 6)

The IALA Guide to the Availability and Reliability of Aids to Navigation input document EEP5/6f/1 was reviewed and amended.  The resulting document (EEP5/output/06) was reviewed and approved by the EEP Committee.

The IALA Draft Recommendation on Availability of Theory and Examples including Comments from Report of Council Session 34, EEP5/6f/2 were reviewed. The Draft Recommendation was crosschecked against the IALA Guidelines on Levels of Service and no conflicts were identified. A liaison note for the ANM Committee, with a proposal for amendments to the IALA Draft Recommendation on Availability of Aids to Navigation Services (EEP5/output/03) was reviewed and approved by the EEP Committee.

Action Items

Secretariat was requested to submit the IALA Guide To Availability And Reliability Theory And Examples (EEP5/output/06) to Council for approval.

Secretariat was requested to forward the proposed revisions to the ‘Draft Recommendation on Availability Objectives of Aids to Navigation Services’ (EEP5/output/03) to ANM5.

## Develop Guidelines on the Methodology of collecting Information on Reliability and Failures of AtoN Equipment (Item 2.2; Task 7)

The Draft IALA Guidelines for Data Collection for AtoN Performance Calculation document (EEP5/output/07) was reviewed and approved by the EEP Committee.

Action Items

Secretariat was requested to submit the ‘IALA Guidelines for Data Collection for AtoN Performance Calculation’ (EEP5/output/07) to Council for approval.

## Revise the guidelines for AtoN Training (Item 2.4)

Preparation of Guidelines on AtoN Training was deferred pending the Training Workshop planned for the Shanghai conference in 2006.

## Monitor the development of the IALA certification process (Item 2.5.4)

Input paper EEP5/6h/3 outlining a road map for the development of additional IALA certification templates was noted.  While it was agreed that the templates are required to make the specification of products similar for all industrial members and to create a level playing field, concern was expressed regarding the format and method of use of the templates.

It was noted by an industrial member that, when developing the templates, it is important to ensure they accommodate manufacturers who make products that are fit for use by the purchaser, but do not necessarily need to meet certain specific tests.  If this is not ensured, these manufacturers may not be certified without cost increase.  In addition, templates should accommodate manufactures who may use national, rather than international, standards.

A draft list of the required IALA Certification templates covering the full range of AtoN equipment was prepared (EEP5/WG2/WP5).  Based upon Standards identified in input paper EEP5/6h/4 and in line with the example template input paper EEP5/6h)/1, members of WG2 are requested to produce templates identifying parameters and tests appropriate to the Product Templates indicated in EEP5/WG2/WP6, as follows:

Action Items

C Baker - Product Template 1 – Lanterns for buoys and light-beacons, including enclosed rotating beacons for EEP6.

C Lagerwall - Product Template 2 – Lighthouse optical systems and components, for use inside lantern houses for EEP6.

A Wilkins - Product Template 3 – Energy sources and related components, including energy generators, energy storage, and regulation or control devices for EEP6.

S Behrens - Product Template 4 – Buoys, buoy moorings, and structures for land use and for offshore for EEP6.

The purpose and status of the Certification Templates, as well as how the templates will be used within the Certification Scheme, was not clear to the Committee.  It was noted that there is no reference to the templates in process 1 and 2 of the certification guideline.  There is minimal reference to the templates in process 3 of the guideline.  A suggested Annex for the Guidelines (EEP5/WG2/WP6) was prepared.

The Working Group considered the request from IALABATT/ IALALITE 5 Workshop EEP5/6h/5 on specification template for self-contained Solar PV Lanterns.  A liaison note (EEP5/output/08) to ANM5 requesting guidance was reviewed and approved by the Committee.

Action Items

Secretariat was requested to forward the draft list of the required IALA Certification templates covering the full range of AtoN equipment (EEP5/WG2/WP5) to EEP6.

Committee Members were requested to review the draft list of the required IALA Certification templates covering the full range of AtoN equipment (EEP5/WG2/WP5) and identify national and international test standards applicable as input for EEP6.

The Secretariat was asked to provide guidance on  the purpose and status of the Certification Templates, as well as how the Templates will be used in the Certification Process, as outlined in EEP5/WG2/WP6, for EEP6.

The Secretariat was asked to forward the liaison note regarding a specification template for self-contained Solar PV Lanterns ( EEP5/output/08) to ANM5.

## Documentation Hierarchy

The Committee noted that there are overlaps in the content of documents and that there are recommendations and guidelines that are being prepared or revised.  The Committee recommend that a table be created, showing the relationships between documents, with a summary of Recommendations and Guidelines currently under review be prepared. M Card agreed to prepare such a table.  The summary should show which Committee is tasked with the preparation and review work.

Action Items

M Card was requested to prepare the table showing the relationships between IALA documents and a summary of Recommendations and Guidelines currently under review as input to EEP6.

# Report from WG 3 – Environment and Publications

WG3 was asked to respond to input papers EEP5/6i/1rev1, EEP5/6i/2, EEP5/61/3, EEP5/6j/1, and EEP5/6j/2.

Action items resulting from EEP4 were reviewed.

## Develop Guidelines on environmental considerations on AtoN engineering (Item 3.1; Task 1)

As per an action item from EEP4, W. Danzik prepared a comprehensive revised draft of the Green Guide, and provided it to WG3 members to review intersessionally.  He incorporated the comments from the WG3 membership and forwarded the document to the Secretariat for posting on the Committee web site.  As requested in EEP4, EEP members were asked to review and provide comments as input to EEP5.  Three input documents were received (listed above).  In addition, comments were received during the work group session from representatives from France and Pharos Marine.  All of this input was reviewed by the working group, and relevant changes were made to the document.

The resulting document, EEP5/output/04, was reviewed and approved by the committee.

Action Item

The Secretariat was asked to forward the Guidelines on environmental considerations in AtoN engineering (EEP5/output/04) to Council for approval.

## Review and update relevant sections of the NAVGUIDE (Item 3.2; Task 5)

The EEP Committee was asked by the ANM Committee to review section 6.2 (per EEP5/6j/2).  The section on hazardous materials was updated.  In consultation with the chairman of WG5 and the EEP chairman, the section referring to the PHL was also updated.

An output document, EEP5/output/05 was reviewed and approved by the committee.

Action Item

The Secretariat was asked to forward the updated section 6.2 of the NAVGUIDE (EEP5/output/05) to the ANM5 Committee as per their request.

## Monitor the development of computer methods and applications to simplify design and management of AtoN (Item 3.3; Task M1)

No work was done on this item during this session.  The WG intends to prepare a summary of all input received to date on this topic, including EEP4/6j/1, as a document to be forwarded to Council prior to the Shanghai Conference.

Action Item

Secretariat was asked to forward EEP4/6j/1, referring to the development of computer methods and applications, to EEP6.

# Report from WG4 – Light and Colour

WG4 was asked to respond to input papers EEP5/6l/1, EEP5/6m/1, EEP5/6n/1, EEP5/6n/2, EEP5/6o/1, EEP5/8/2,EEP5/8/3,and EEP5/8/4.

Action items resulting from EEP4 were reviewed.

## Develop Guidelines on Ambient Light Levels (Item 4.1; Task 3)

The Guideline on Ambient light levels EEP5/6l/1was reviewed. The Guideline was amended and approved by the Committee and issued as an output paper EEP5/output/09 for submission to Council for approval.

It was noted that the ambient switching levels for AtoN lights referred to in the Navguide are not specified but are left to the National Authorities.  Consequently a note was prepared for ANM committee, EEP5/output/14, requesting that this part of the Navguide reflects the switching levels in the new Guidelines on Ambient Light Switching Levels.

Action Items

The Secretariat was asked to forward the IALA Guide To Ambient Light Levels At Which AtoN Lights Should Switch On And Off, EEP5/output/09, to Council for approval.

The Secretariat was requested to submit liaison note EEP5/output/14 to ANM5, requesting updating of the Navguide in line with the Guidelines on Ambient Light Levels At Which AtoN Lights Should Switch On And Off, if the Guidelines are approved by Council.

## Develop Guidelines on Sector Lights and Sector Projection Lights (Item 4.2; Task 4)

The Guidelines on Sectors, Sector Lights EEP5/6m/1 were reviewed and amended. Output document EEP5/output/12 was reviewed and approved by the Committee for forwarding to Council.

Action Items

The Secretariat was requested to forward the IALA Guidelines on Sectors Lights, EEP5/output/12, to Council for approval.

## Study the Spectral and Spatial Characteristics of new and developing new lights. (Item 4.3; Task 14)

Input papers EEP5/6n/1 and EEP5/6n/2 were noted. The main task under Item 4.3 is to develop guidelines on a method of specifying LED lanterns. It was noted that there is a significant amount of data and papers on the subject of LEDs, including input and output papers of past EEP meetings. P.C. To and Lu Yongqiang were requested to review the available documents and produce a paper summarising the information as an input paper to EEP6. To assist this process the working group drew up an outline structure for the paper, EEP5/WG4/WP5.

A request, EEP5/8/3, for information on LEDs and lighthouse categorisation from Peru was reviewed. A response answering two questions was drafted, EEP5/output/13. The Secretariat was requested to forward the draft response to ANM5 for a response to the third questions and reply to the Peruvian Hydrographic Office.

Action Items

P.C. To and Lu Yongqiang were requested to review the available documents and produce a paper summarising available LED information as an input paper to EEP6.

The Secretariat was requested to forward the draft response to the question from Peru (EEP5/output/13) to ANM5 for a response to the third question and then prepare the reply to the Peruvian Hydrographic Office.

## Monitor international progress on colours of light signals (Item 4.4. Task M3)

The liaison input paper EEP5/8/2 from ANM on the use of Blue Lights for AtoN was reviewed. It was agreed that C Baker should review the ‘IALA recommendation for the Colours of Light Signals on Aids to Navigation’ December 1977 and update the recommendation to comply with CIE Standards with particular attention to chromaticity coordinates for blue lights.  This work will be coordinated with the work of the Proposed Specialist Working Group on Colours of Light Signals, calculation of the effective intensity of flashed lights and the determination of luminous intensity.

Input document EEP5/8/4 was noted.  The Committee noted that, during the IALABATT / IALALITE 5 workshop, E-122 Recommendation on Photometry was updated and references to colour were removed. The working group felt that guidance on colour measurement is required. The working group recommend that a specialist working group be set up to amend and amalgamate the 1977 IALA Recommendation on colour signals, 1977 IALA Recommendation on Luminous Intensity, 1980 IALA Recommendation of the Calculation of the Effective Intensity of Rhythmic Light and E122 IALA Recommendation on Photometry of Marine Aids to Navigation (Draft - Dec 2004). It was suggested that draft IALA Recommendation(s) on optical performance be prepared for consideration by EEP6 with a final review at EEP7, if required.  A draft terms of reference for a Specialist Working Group on colours of light signals, calculation of the effective intensity of flashed lights and the determination of luminous intensity, EEP5/output/15, was prepared. The Secretariat was requested to coordinate the setting up of the Specialist Working Group.

Action Items

C Baker was asked to review the IALA Recommendations of Light Signals on Aids to Navigation’ December 1977 and update it to comply with the CIE equivalent standard and to coordinate this work with the proposed specialist working group on Colours Of Light Signals, Calculation of the Effective Intensity of Flashed Lights.

The Secretariat was requested to coordinate the setting up of a Specialist Working Group on Colours Of Light Signals, Calculation of the Effective Intensity of Flashed Lights and the Determination of Luminous Intensity in accordance with the terms of reference EEP5/output/15.

## Add graphical representation and numerical examples of light characters to Chapter 3 of the Navguide, taking account of EEP4/2/2 (item 4.6.5).

Input paper EEP5/6o/1 ‘Light Characteristics for Admiralty List of Lights’ was reviewed.

It was agreed that IALA Recommendation E110, Rhythmic Characters of Flashing Lights and Navguide section 3.4.3 ‘Rhythms/Character Table’ should be updated and graphical representation of light characters included, together with numerical examples, in accordance with the United Nation SIGNI Recommendation. C Martinez and V Rinaldi were asked to update E110 and Navguide section 3.4.3 in accordance with the UN SIGNI Recommendation and submit as input to EEP6.

Action Item

C Martinez and V Rinaldi were asked to update E110 and Navguide section 3.4.3 in accordance with the UN SIGNI Recommendation and submit as input to EEP6.

# Report from WG 5 - Preservation of Historic Lighthouses

WG5 was asked to respond to input papers EEP5/6p)/1, EEP5/6q)/1 and EEP5/8/5.

Action items from EEP4 were reviewed.

## Developments in Lighthouse Preservation

Discussions on the Preservation of Historic Lighthouses included a session where the latest developments on Lighthouse Preservation in the countries represented were presented and are included at Annex 9, along with related documents.

## Develop means of recording and documenting changes in the history of lighthouses (Item 5.1.2; Task 10)

- Approved by council at session 34.  This has now been incorporated in the Preservation Manual as Chapter 8.

## Develop Guidelines on managing the consequences of technical change (Item 5.1.3; Task 11)

- Further work on the document ‘Managing the consequences of technical change’ – Chapter 7 of the manual was carried out at EEP 5 and a second draft produced (EEP5/WG5/WP1). This draft is considered near completion and WG 5 expects that this will be forwarded to council after EEP 6.

- Action Items

- The Secretariat was asked to forward the chapter on managing the consequences of technical change – Chapter 7 (EEP5/WG5/WP1) to EEP6.

- WG5 members were asked to review the chapter on managing the consequences of technical change – Chapter 7 (EEP5/WG5/WP1) for EEP6.

## Develop – IALA web site portal relating to historic lighthouses for public relations purposes (Item 5.2; Task 12)

Since EEP 4, IALA Secretariat has gained the necessary expertise related to the interactive template and are now prepared to move forward with the trials. The secretariat expects that there may be an opportunity to expand the database and to provide additional information to users.

- Action Items

- The Secretariat was asked to provide a report to EEP 6 on the results of the trials on the interactive template for the IALA web site portal relating to historic lighthouses for public relations purposes.

## Develop Chapter on experience gained – Do’s and Don’ts of Preservation of Historic Lighthouses (Item 5.1.5)

- Following EEP 3 a first draft of this chapter was prepared and circulated as an input document to EEP 5 for review and discussion. Further work on the document ‘Do’s and Don’ts of Preservation of Historic Lighthouses’ – Chapter 9 of the manual (EEP5/6r/1), will be carried out at EEP 6.

- Action Items

- The Secretariat was asked to forward the chapter on Do’s and Don’ts of Preservation of Historic Lighthouses – Chapter 9 (EEP5/6q/1) to EEP6.

- WG5 members were asked to prepare further input to the chapter on Do’s and Don’ts of Preservation of Historic Lighthouses – Chapter 9 (EEP5/6q/1) for EEP6.

## Develop subject matter for a possible seminar on the practical aspects of lighthouse preservation (Item 5.4.1)

Council approved the Seminar proposals and agreed that it will be held in Gothenburg August 16 – 19 2005. A steering committee meeting took place in Gothenburg this past August and a second meeting was held at EEP 5. The list of speakers, seminar objectives and detailed programme were reviewed and are expected to be completed by mid December.  The EEP Committee will be informed as the Seminar develops.

## PHL/EEP Merger Evaluation

At EEP4, the WG was tasked by the committee chair to evaluate the current working arrangements within the EEP structure of what was previously known as the PHL (EEP4/WG5/WP1).

After considerable review and discussion it was concluded that WG5 continue as part of the EEP committee structure.

Action Item

The Chairman of EEP was asked to raise the concerns over PHL/EEP merger(as identified in EEP4/WG5/WP1) at the next meeting of the PAP and report back at EEP 6.

## Wicklow Lighthouse Technical Visit

The WG visited Wicklow Head Irish Landmark Trust Tower and was tasked by the Committee Chair to use this visit as an opportunity to develop a Methodology for Case Study Evaluation. A first draft of a methodology framework was produced (EEP 5/WG 5/WP 3). This document is expected to become an annex to the Manual on Lighthouse Preservation.

Action Item

Secretariat was asked to forward the draft template on a Methodology for Case Study Evaluation (EEP5/WG5/WP3) to EEP 6

Secretariat was asked to include documents relating to the Wicklow Head Lighthouse and Hook Head Lighthouse visits in the final report for EEP 5.

- WG5 members were asked to prepare further input to the document Methodology for Case Study Evaluation (EEP5/WG5/WP3) for EEP6.

## Letter from John Hopkins, Consultants

The working group was tasked by the committee chair to prepare a draft response to Mr Hopkins for sign off by the Secretary General. A draft response (EEP5/output/02) was prepared and submitted to the Secretariat.

Action Item

The Secretariat was asked to format the draft response to John Hopkins (EEP5/output/02) and forward to Mr Hopkins, by October 21, 2004.

# Any Other Business

## IALA Conference 2006 Call for Papers

The Committee discussed the need to submit abstracts for presentation at the conference by the deadline of October 29, 2004.  It was suggested by the Chair of WG 5 that two abstracts be produced specifically relating to the importance of its work on Lighthouse Preservation on behalf of IALA.

Action Item

Members were asked to note the deadline for submissions of abstracts for papers for the IALA 2006 Shanghai Conference.

## Work Items for 2006-2010 work term

The process of work programme items, and the working process for IALA Committees from 2006-2010 was discussed.  The Chairman noted that the focus of the Oct. 2004 PAP meeting will be to begin discussions on the working process from 2006-2010.

Action Item

Members were asked to consider work program items for the work term 2006-2010 for input to EEP6.

## Dublin Observation – LED and Incandescent lights

During the meeting participants were asked to take part in an experiment to see if there were differences in perception of LED and incandescent lights.  This experiment was similar to the experiment carried out during IALABATT/IALALITE5.  The results of this experiment supported those from the workshop.

In conclusion, the results of the Dublin observations indicate that low intensity colour LED based light sources are not perceived brighter than incandescent based light sources (under the conditions of the test).

Action Item

The Secretariat was asked to post the results presentation of the Dublin Observation (LED and incandescent lights) to the IALA Committee web site.

## Session Closing

As there was no further business, the Chairman closed EEP5 and thanked all members for their participation during the week.  He noted that significant work that had been completed and wished all members a safe trip home.  In closing, he thanked CIL for hosting the meeting, especially Seamus Doyle, Fiona Lee and Pauline MacMahon.

Participants were reminded that EEP6 will be held from April 4-8, 2005 at IALA Head-Quarters in Saint Germain en Laye, France.

Annex 1 - IALA Committee Agenda EEP5

| EEP Committee 5th session Agenda item 1 | EEP5/1/1rev1 |
| --- | --- |

The 5th meeting of the EEP Committee will be held from October 4- 8, 2004 at Clontarf Castle Hotel, Dublin, Ireland. The opening plenary will commence at 1300 on Monday, October 4 and the closing plenary will end at approximately 1300 on Friday, October 8.  Committee Chair, Vice-chair and working group Chairpersons are requested to meet at 1000 on Monday October 4, 2004.

## AGENDA

- Approval of the agenda.

- Review of action items from EEP4.

- Review of input papers.

- Reports from other bodies:

4.1	IALA Council

4.2	IMO

4.3	Other input as appropriate

- Report from Rapporteurs for items to be monitored

5.1	Developments in AtoN (Item 1.3, M2);

5.2	International progress on colours of light signals, calculations of the effective intensity of flashing lights and determination of luminous intensity (Item 4.5, M3);

5.3	Development on renewable energy sources (Item 1.3, M4).

- Work Programme

- Work Programme related Items

- Develop Guidelines on maintenance practices for buoys and small fixed Aids to Navigation structures, including signal equipment (Item 1.1, Task 2).

- Revise Guidelines on Battery Handling and Maintenance (Item 1.5, Task 15*).

- 6d)Provide guidance on the practicability of a universal IALA Solar Design program based on functional specification (Item 1.6, Task 16*).

- Prepare guidelines on the methodology for cost benefit analysis of different types of buoys, if time permits. (Item 1.8.8)

- Revise Guidelines on Quality Assurance, Availability of systems and components (Item 2.1, Task 6*).

- Develop Guidelines on the Methodology of Collecting Information on Reliability and Failures of AtoN Equipment (Item 2.2, Task 7*).

- Produce additional certification templates (Item 2.5.4).

- Develop Guidelines on Environmental Considerations of AtoN Engineering (Item 3.1, Task 1*).

- Review and Update Relevant Sections of the Navguide (Item 3.2, Task 5*).

- Provide a report on the availability of computer methods and applications to simplify design and management of AtoN (Item 3.3, Task M1*);

- Develop Guidelines on Ambient Light Levels at which AtoN Lights should switch on and off (Item 4.1, Task 3*).

- Develop Guidelines on Sectors, Sector Lights and Sector Projection Lights (Item 4.2, Task 4*).

- Study the Spectral and Spatial Characteristics of New and Developing New Lights (Item 4.3, Task 14*).

- Add graphical representation of light characters to Chapter 3 of the Navguide, taking account of EEP4/2/2 (Item 4.6.5).

- Develop Chapter on managing the consequences of Technical Changes (Item 5.1.3, Task 11*).

- Develop Chapter on experiences gained - Do’s and don’ts of Preservation of AtoN (Item 5.1.5).

- Review of output and working papers.

- Any other business.

- Review of session report.

Members are requested to provide comments or proposals on any of the above items to the Secretariat by not later than September 4, 2004.

Documents received by the Secretariat will be published on the Committee web-site normally within three working days of receipt.

Note – items marked with an asterix (*) reflect the Task Number referenced in the Proposed Work Programme as approved by IALA Council.

Annex 2 – EEP5 Participants

| Country | Organisation / Name | Contact numbers |
| --- | --- | --- |
| Belgium | Ministry of the Flemish Community Mr. Dirk Gunst Sir Winston Churchillkaai, 2 B-8400 Oostende | Phone: 32 59 56 63 60 Fax: +32 59 56 63 15 e-mail: dirk.gunst@lin.vlaanderen.be |
| Canada | Canadian Coast Guard Mr. Roger Beauchesne DFO/CCG Integrated Technical Services 200 Kent Street Station 6W090 Ottawa, Ontario K1A 0E6 | Phone: +1 613 998 1404 Fax: +1 613 998 9258 e-mail: beauchesner@dfo-mpo-gc.ca |
|  | Canadian Coast Guard Mr. Larry Wilson Maritimes Region 176 Portland Street Dartmouth, NS B2Y 1J3 | Phone: +1 902 426 3907 Fax: +1 902 426 4312 e-mail: wilsonl@mar.dfo-mpo.gc.ca |
| China | Shanghai Maritime Safety Administration of P.R.C. Mr. LU Yongqiang 190 Siping Road Shanghai 200086 | Phone: +86 21 53931557 Fax: +86 21 53931500-1351 e-mail: luyongqiang@shmsa.gov.cn |
|  | Tianjin Maritime Safety Administration of P.R.C. Mr. SHEN Zhi Jiang 34, Hei Nu Cheng Road HeXi District Tianjin, 300211 | Phone: +86 22 25711162-291 Fax: +86 22 66310617 e-mail: northsea@enorth.com.cn |
| Hong Kong, China | Hong Kong Marine Department Mr. Kwong-Chun CHAN Harbour Building 38 Pier Road Central Hong Kong | Phone: +852 2852 4454 (direct) Fax: +852 2545 1535 (direct) e-mail: kc_chan@mardep.gov.hk |
| Denmark | Royal Administration of Navigation and Hydrography Mr. Omar Frits Eriksson (Committee Chair) Overgaden oven Vandet 62 B P.O. Box 1919 1023 Kobenhavn K | Phone: +45 32 689 598 Fax: +45 32 689 634 e-mail: ofe@frv.dk |
|  | OI Electric A/S Mr. Ove Ibsen Hørretvej 61 DK 8320 Mårslet | Phone: +45 87 37 64 00 Fax: +45 86 29 48 44 e-mail: oi@oielectric.dk |
| England | Trinity House Lighthouse Service Mr. Clive Baker Principal Electrical & Radio Engineer East Cowes Isle of Wight PO32 6RE | Phone: +44 1983 203 408 Fax: +44 1983 294 317 e-mail: clive.baker@thls.org |
|  | Pharos Marine Mr. Adrian Wilkins Consultant with Pharos Marine 65 Sylvan Avenue East Cowes Isle of Wight PO32 6QS | Phone: +44 1983 297958 e-mail: adrianwilkins@talk21.com |
|  | Trinity House Lighthouse Service Philip Hyde East Cowes Isle of Wight PO32 6RE | Phone + 44 1983 20 34 Fax + 44 1983 29 43 17 e-mail phil.hyde@thls.org |
| Finland | Finnish Maritime Administration Waterways Department Mr. Risto Joro P.O. Box 171 FI-00181 Helsinki | Phone: +358 20 448 4330 Fax: +358 20 448 4680 e-mail: risto.joro@fma.fi |
| France | CETMEF Mr. Guy Cunty B.P. 543 2 Avenue du Président Kennedy 13092 Aix en Provence cedex 2 | Phone: +33 4 42 52 74 25 Fax: +33 4 42 52 74 01 e-mail: guy.cunty@equipement.gouv.fr |
|  | CETMEF Mr. Joël Tourbot Technopôle Brest Iroise BP 5 29280 Plouzané | Phone : +33 2 98 05 67 78 Fax : +33 2 98 05 67 67 e-mail : joel.tourbot@equipement.gouv.fr |
| Germany | Wasser-und Schifffahrtsverwaltung WSV Mr. Stefan Behrens Mozartstrasse 32 26382 Wilhelmshaven | Phone: +49 4421 186 340 Fax: +49 4421 186 308 e-mail: behrens@whv.wsdnw.de |
|  | Wasser- und Schifffahrtsverwaltung WSV, Fachstelle für Verkehrstechniken (FV) Mr. Jörg Unterderweide Technische Dienste Weinbergstrasse 11-13 56070 Koblenz | Phone + 49 261 9819 2400 Fax + 49 261 9819 2155 E-mail Junterderweide@fvt.wsv.de |
| Ireland | Commissioners of Irish Lights Mr. James Doyle Engineering Operations Manager Harbour Road Dun Laoghaire, Co. Dublin | Phone: +353 1 214 5710 Fax : +353 1 280 7954 e-mail : s.doyle@cil.ie |
| Italy | Italian Navy NAVISPELOG 4° Reparto Fari Captain Vincenzo Rinaldi Via Taormina 4 00135 Roma | Phone: +39 06 36807193 Fax: +39 06 36807208 e-mail: navlog.4r.capo1uff@marina.difesa.it |
|  | Italian Navy NAVISPELOG 4° Reparto Fari Lieutenant Davide Conti Via Taormina 4 00135 Roma | Phone: +39 06 36807212 Fax: +39 06 36807208 e-mail: ispefari@libero.it, or navlog.4r.ad1uff@marina.difesa.it |
| Japan | Japan Aids to Navigation Association (JANA) Mr. Yashuhiro Abe Kaiji-Center Bldg. 4-5 Kouji-Machi Chiyoda-ku Tokyo 102-0083 | Phone: +81 3 3230 1470 Fax: +81 3 3230 1050 e-mail: yasuhiro-abe@jana.or.jp |
|  | Ryokuseisha Corporation Mr. Mitsuo Horiguchi Tsukiji 2-15-14 Chu-ku Tokyo | Phone: +81 3 3542 4751 Fax: +81 3 3542 4757 e-mail: ryokusei@ryokusei.co.jp |
|  | Zeni Lite Buoy Co., Ltd. Mr; Michael D. Card P.O. Box 54 East Horsley KT24 5YD United Kingdom | Phone (UK): +44 1483 281344 Phone (Japan): +81 80 30 58 65 43 Fax: +44 1483 281355 e-mail : mike.card@zenilite.co.uk |
| Netherlands | Directorate General of Public Works and Water Management Mr. Sipke Hoekstra North Sea Directorate P.O. Box 5807 2280 HV Rijswijk | Phone: +31 70 33 66600-884 Fax: +31 70 415 22 46 e-mail: s.hoekstra@dnz.rws.minvenw.nl |
| Scotland | Northern Lighthouse Board Mr. Bob McIntosh 84 George Street Edinburgh EH2 3DA | Phone: +44 1314 73 31 61 Fax: +44 1312 20 20 93 e-mail: bobm@nlb.org.uk |
|  | Northern Lighthouse Board Mr. Moray Waddell 84 George Street Edinburgh EH2 3DA | Phone: +44 1314 73 31 50 Fax: +44 1312 20 20 93 e-mail: morayw@nlb.org.uk |
| Spain | Puertos del Estado Mrs. Carmen Martinez Avda. del Partenon, 10 28042 Madrid | Phone: +34 91 524 55 26 Fax: +34 91 524 55 04 e-mail: cmartinez@puertos.es |
|  | Puertos del Estado (Santander Port Authority) Mr. Carlos Calvo Dique de Gamazo S/N Santander | Phone: +34 942 81 00 34 e-mail: carloscgmja@telelines.es |
|  | La Maquinista Valenciana SA Mr. Fernando Romero Ronda Isaac Peral 4 Parque Tecnologico de Valencia 46980 Paterna | Phone : +34 96 1402174 Fax : +34 96 1400962 e-mail : fernando.romero@lmvsa.com |
| Sweden | National Maritime Administration Mr. Christian Lagerwall S-601 78 Norrköping | Phone: +46 11 191193 Fax: +46 11 191230 e-mail: Christian.lagerwall@sjofartsverket.se |
| USA | US Coast Guard (G-SEC-2) Mr. Wayne Danzik 2100 2nd Street SW Washington DC 20593-0001 | Phone: +1 202 267 1898 Fax: +1 202 267 4788 e-mail: wdanzik@comdt.uscg.mil |
|  | Tideland Signal Corporation Mr. P.C. To 4310 Directors Row Houston, Texas 77092 | Phone: +1 713 681 6101 Fax: +1 713 681 6233 e-mail: pcto@tidelandsignal.com |
| IALA | IALA-AISM Mrs. Jillian Carson Jackson Mrs. Marie-Hélène Grillet 20ter rue Schnapper 78100 Saint Germain en Laye France | Phone: +33 1 34 51 70 01 Fax: +33 1 34 51 82 05 e-mail: jillian.carson@wanadoo.fr mariehelene.grillet@wanadoo.fr |

Annex 3 – Working Group Participants

WG1

| Name | Organisation |
| --- | --- |
| Adrian Wilkins | Pharos Marine (Chairman) |
| Wayne Danzik | US Coast Guard (Rapporteur) |
| Sipke Hoekstra | North Sea Directorate |
| Stefan Behrens | Wasser- und Schifffahrtsverwaltung |
| Moray Waddell | Northern Lighthouse Board |
| Chan Kwong Chun | Hong Kong Marine Department |
| Jorg Unterderweide | Wasser- und Schifffahrtsverwaltung |
| Roger Beauchesne | Canadian Coast Guard |
| Joel Tourbot | CETMEF |
| Carlos Calvo | Santander Port Authority, Spain |
| Shen Zhi Jiang | China MSA |
| Ove Ibsen | OI Electric |

WG2

| Name | Organisation |
| --- | --- |
| Baker, Clive | THLS, England |
| Doyle, Seamus | Commissioners of Irish Lights, Ireland |
| To, P.C. | Tideland Signal Corporation, USA |
| Behrens, Stefan | Wasser- und Schifffahrtsverwaltung |
| Joro, Risto | Finnish Maritime Administration, Finland |
| Tourbot, Joel | CETMEF, France |
| Lagerwall, Christian | Swedish Maritime Agency, Sweden |
| Hoekstra, Sipke | Netherlands DNZ, Netherlands |
| Waddell, Moray | Northern Lighthouse Board, Scotland |
| Wilkins, Adrian | Pharos Marine, England |
| Ibsen, Ove | OI Electric, Denmark |
| Card, Michael | Zeni Lite Buoy Co. Ltd., Japan |
| Shen, Zhi Jiang | China Maritime Safety Administration, China |
| Horiguchi, Mitsuo | Ryokuseisha Corporation, Japan |
| Abe, Yasuhiro | JANA, Japan |
| Romero, Fernando | La Maquinista, Spain |

WG3

| Name | Organisation |
| --- | --- |
| Roger Beauchesne | CCG (Chair) |
| Wayne Danzik | USCG (Rapporteur) |
| Chan Kwong Chun | Hong Kong Marine Department |
| Carlos Calvo | Santander Port Authority, Spain |
| Vincenzo Rinaldi | Italian Navy |
| Davide Conti | Italian Navy |
| Lu Yongqiang | China MSA |

WG4

| Name |  | Organisation |  |
| --- | --- | --- | --- |
| DOYLE Seamus |  | Commissioners of Irish Lights, Ireland |  |
| TO P.C. |  | Tideland Signal Corporation, USA |  |
| CARD Michael |  | Zeni Lite Boy Co Ltd, Japan |  |
| BAKER Clive |  | Trinity House, England |  |
| ROMERO Fernando |  | La Maquinista Valenciana, Spain |  |
| CONTI Davide |  | Italian Navy |  |
| ABE Yasuhiro |  | JANA, Japan |  |
| LAGERWALL Christian |  | Swedish Maritime Administration, Sweden |  |
| RINALDI, Vincenzo |  | Italian Navy |  |
| JORO Risto |  | Finnish Maritime Administration, Finland |  |
| IBSEN Ove |  | Oi-Electric, Denmark |  |
| MARTINEZ Carmen |  | Puerto del Estado, Spain |  |
| Lu Yongqiang | China MSA |  |  |

WG5

| Name | Organisation |
| --- | --- |
| Larry Wilson | Canadian Coast Guard (chairman) |
| Philip Hyde (Part) | Trinity House, England |
| Bob McIntosh | Northern Lighthouse Board, Scotland |
| Guy Cunty | CETMEF, France |
| Marie Helene Grillet | IALA Secretariat |
| Carmen Martinez | Puertos del Estado, Spain |
| Christian Lagerwall (Part) | Swedish Maritime Administration, Sweden |
| Dirk Gunst | Ministry of Flemish Community |
| LU Yongqiang (Part) | China MSA |
| Vincenzo Rinaldi (Part) | Italian Navy |

Annex 4 – List of Input papers Session 5, Oct. 4-8, 2004

Items highlighted in Yellow were not posted to web site.

Agenda item 1 – Approval of Agenda

| Number | Title / Author (if required) | WG |
| --- | --- | --- |
| EEP5/1/1 | Agenda | NA |

Agenda item 2 – Review of Action Items – EEP1

| Number | Title / Author (if required) | WG |
| --- | --- | --- |
| EEP5/2/1 | (except from Report, EEP3) Action Items | N/A |

Agenda item 3 – Review of Input Papers

| Number | Title / Author (if required) | WG |
| --- | --- | --- |
| EEP5/3/1rev1 | Input paper list | N/A |

Agenda item 4 – Reports from other Bodies

| Number | Title / Author (if required) | WG |
| --- | --- | --- |
| EEP5/4/1 | Council Report Session 34 | NA |
| EEP5/4/2 | IMO report MSC78 (from JCLeclair) | NA |
| EEP5/4/3 | IMO report – NAV50 |  |
| EEP5/4/4 | IALA Submission to NAV50 – IALA Risk Assessment Tool |  |
| EEP5/4/5 | Report from Working Group on Aids to Navigation Information Service (ANIS) |  |
| EEP5/4/info1 | Draft report of IALABATT/IALALITE 5 Workshop (Conclusions and Recommendations) |  |

Agenda Item 5 – Reports from Rapporteurs

| Number | Title / Author (if required) | Presented by: |
| --- | --- | --- |
|  | Developments in AtoN (M2) | NA |
|  | International progress on colours of light signals, calculations of the effective intensity of flashing lights and determination of luminous intensity (M3) | OE - verbal |
|  | Development on renewable energy sources (M4). | AW - verbal |

Agenda item 6 –  Work Programme

6 a)	Work Programme Related Items

| Number | Title / Author (if required) | Working Group |
| --- | --- | --- |
| EEP4/6a/1 | Detailed Work Program | NA |

6b)	Develop Guidelines on maintenance practices for buoys and small fixed Aids to Navigation structures, including signal equipment (Item 1.1, Task2)

| Number | Title / Author (if required) | WG |
| --- | --- | --- |
| EEP5/6b/1 | Draft Guidelines on the Maintenance of Buoys and Small AtoN Structures / W. Danzik | 1 |

6c)	Revise Guidelines on Battery Handling and Maintenance (Item 1.5).

| Number | Title / Author (if required) | WG |
| --- | --- | --- |
| EEP5/6c/1 | Draft Guidelines On Secondary Batteries For Aids To Navigation | 1 |

6d)	Provide guidance on the practicability of a universal IALA Solar Design program based on functional specification (Item 1.6, Task 16)

| Number | Title / Author (if required) | WG |
| --- | --- | --- |
| EEP5/6d)/1 | IALA Solar Sizing Program | 1 |
| EEP5/6d)/2 | Draft End User Agreement for IALA Solar Sizing Program / Secretariat | 1 |
| EEP5/6d)/3 | Comments on Solar Sizing Program (Spain) | 1 |

6e)	Prepare guidelines on the methodology for cost benefit analysis of different types of buoys, if time permits. (Item 1.8.8)

| Number | Title / Author (if required) | WG |
| --- | --- | --- |
| EEP5/6e)/1 | A methodology for Cost Benefit Analysis of buoys / O. Eriksson | 1 |
|  | Note – paper EEP5/8/1 also refers |  |

6 f)	Revise Guidelines on Quality Assurance, Availability of systems and Components (Item 2.1, Task 6).

| Number | Title / Author (if required) | WG |
| --- | --- | --- |
| EEP5/6f)/1 | Draft - IALA Guide To Availability And Reliability Theory And Examples / C. Baker | 2 |
| EEP5/6f/2 | RNAV Liaison note - Definitions of Availability, Continuity and Integrity (for discussion purposes only) | 2 |
| EEP5/6f/info 1 | Reliability and Maintainability Definitions – NATO / C. Baker | 2 |
| EEP5/6f)/info 2 | Reliability and Maintainability Definitions – UK MOD / C. Baker | 2 |

6g)	Develop Guidelines on the Methodology of Collecting Information on Reliability and Failures of AtoN Equipment (Item 2.2, Task 7).

| Number | Title / Author (if required) | WG |
| --- | --- | --- |
| EEP5/6g)/1 | Draft Guidelines on Data Collection for AtoN Performance Calculation / C. Baker | 2 |

6h)	Produce additional certification templates (Item 2.5.4).

| Number | Title / Author (if required) | WG |
| --- | --- | --- |
| EEP5/6h/1 | Certification Template as produced at EEP3 | 2 |
| EEP5/6h/info1 | IALA Certification Guideline (as approved by IALA Council) | 2 |
| EEP5/6h/2 | Work from WG2, ENG12 on Certification Templates | 2 |
| EEP5/6h/3 | On the development of additional IALA Certification Templates / O. Eriksson | 2 |
| EEP5/6h/4 | Some International Performance Test Standards / C. Baker, O. Eriksson | 2 |
| EEP5/6h/5 | Note from IALALITE/IALABATT 5 on specification template for self-contained Solar PV Lanterns | 2 |

6i)	Develop Guidelines on Environmental Considerations of AtoN Engineering (Item 3.1, Task 1).

| Number | Title / Author (if required) | WG |
| --- | --- | --- |
| EEP5/6i)/1rev1 | Draft ‘Green Guide’ | 3 |
| EEP5/6i)/2 | Comments on the draft ‘Green Guide’ / Spain | 3 |
| EEP5/6i)/3 | Detailed comments on Green Guide / Santander Port Authority (Spain) | 3 |

6j)	Review and Update Relevant Sections of the NAVGUIDE (item 3.2, Task 5)

| Number | Title / Author (if required) | WG |
| --- | --- | --- |
| EEP5/6j/1 | Status of Navguide Review from ANM | 3 |
| EEP5/6j/2 | Chapter 6 of Navguide for Review / ANM Committee | 3 |

6k)	Provide a report on the availability of computer methods and applications to simplify design and management of AtoN (Item 3.3, Task M1)

| Number | Title / Author (if required) | WG |
| --- | --- | --- |
|  | No input paper | 3 |

6l)	Develop Guidelines on Ambient Light Levels at which AtoN Lights should switch on and off (Item 4.1, Task 3)

| Number | Title / Author (if required) | WG |
| --- | --- | --- |
| EEP5/6l/1 | Draft Guideline on Ambient light levels as amended through intersessional work / S. Doyle | 4 |

6m)	Develop Guidelines on Sectors, Sector Lights and Sector Projection Lights (Item 4.2, Task 4)

| Number | Title / Author (if required) | WG |
| --- | --- | --- |
| EEP5/6m/1 | Draft Guideline on Sector Lights / as amended through intersessional work | 4 |

6n)	Study the Spectral and Spatial Characteristics of New and developing New Lights (Item 4.3, Task 14)

| Number | Title / Author (if required) | WG |
| --- | --- | --- |
| EEP5/6n/1 | Experience regarding the effect of aging on LED life / Spain (C. Martinez) | 4 |
| EEP5/6n/2 | LED Life tests in Netherlands / S. Hoekstra | 4 |

6o)	Add graphical representation of light characters to Chapter 3 of the Navguide, taking account of EEP4/2/2 (Item 4.6.5).

| Number | Title / Author (if required) | WG |
| --- | --- | --- |
| EEP5/6o/1 | Light Characteristics from Admiralty List of Lights / S. Doyle | 4 |

6p)	Develop Chapter on managing the consequences of Technical Changes (Item 5.1.3, Task 11*).

| Number | Title / Author (if required) | WG |
| --- | --- | --- |
| EEP5/6p)/1 | Draft Chapter – Managing the consequences of technical changes Formerly EEP4/6q/1 | 5 |

6q)	Develop Chapter on experiences gained - Do’s and don’ts of Preservation of AtoN (Item 5.1.5).

| Number | Title / Author (if required) | WG |
| --- | --- | --- |
| EEP5/6q)/1 | Draft – Do’s and Don’ts of Preservation Formerly EEP4/6r/1 | 5 |

Agenda item 7 – Review of output and working papers

Agenda item 8 – Any Other Business

| Number | Title / Author (if required) | WG |
| --- | --- | --- |
| EEP5/8/1 | Advantages and Disadvantages in the use of large plastic buoys (1.8 to 3.0m diameter) / A Wilkins (in response to EEP4/10/1 ) | 1 |
| EEP5/8/2 | Liaison from ANM on the Colour Signal Standard on Blue Lights / formerly ANM4/output/03 | 4 |
| EEP5/8/3 | Letter from Peru regarding LEDs | 4 |
| EEP5/8/4 | Revisions to E-122 on Photometry (as per work item 4.4) | 4 |
| EEP5/8/5 | Letter from John Hopkins for information on documentation related to fresnel lenses | 5 |

Annex 5 – List of Output and Working Papers

Output documents are submitted for review by a body other than the Committee initiating the document.

| Number | Title | Status |
| --- | --- | --- |
| EEP5/output/01 | Left Blank | -- |
| EEP5/output/02 | Response to John Hopkins | Approved Forward to John Hopkins |
| EEP5/output/03 | Liaison to ANM5 - Review of Draft Recco. On Availability Objectives | Approved Forward to ANM5 |
| EEP5/output/04 | Draft IALA Guideline on Environmental Considerations In AtoN Engineering | Approved Forward to Council |
| EEP5/output/05 | Liaison to ANM5 - Review of Navguide Chapter 6.2 | Approved Forward to ANM5 |
| EEP5/output/06 | Draft IALA Guide To Availability And Reliability - Theory And Examples | Approved Forward to Council |
| EEP5/output/07 | Draft IALA Guidelines On Data Collection for AtoN Performance Calculation | Approved Forward to Council |
| EEP5/output/08 | Liaison Note to ANM on LED and Self Contained Lanterns | Approved Forward to ANM5 |
| EEP5/output/09 | - Draft Guidelines for the Ambient Light Levels at which AtoN Lights Should Switch On And Off | Approved Forward to Council |
| EEP5/output/10 | Draft Guidelines on Solar Sizing | Approved Forward to Council |
| EEP5/output/11 | Draft Guideline on Maintenance of Small Buoys and Small AtoN Structures | Approved Forward to Council |
| EEP5/output/12 | Draft IALA Guidelines Sector Lights | Approved Forward to Council |
| EEP5/output/13 | Liaison note to ANM re the question from Peru | Approved Forward to ANM5 |
| EEP5/output/14 | Liaison note to ANM regarding draft IALA Guideline on Ambient Light Levels | Approved Forward to ANM5 |
| EEP5/output/15 | Draft ToR for Specialised Working Group on colours of light signals, calculations of the effective intensity of flashed lights and the determination of luminous intensity | Approved Forward to Secretariat |
| EEP5/output/16 | Report of EEP5 | Reviewed and approved as amended |

Working Papers are documents that will remain within the committee for further review.

| Number | Title | Status |
| --- | --- | --- |
| EEP5/WG2/WP5 | IALA Certification Templates | Working Paper / Forward to EEP6 |
| EEP5/WG2/WP6 | Purpose of IALA Certification Templates | Forward to Secretariat for Clarification / Forward to EEP6 |
| EEP5/WG4/WP5 | LED Status | Working Paper / Forward to EEP6 |
| EEP5/WG5/WP1 | Chapter Preservation Manual – Technical Change | Working Paper (Final draft) / Forward to EEP6 for completion |
| EEP5/WG5/WP3 | Methodology for Case Study Evaluation | Working Paper / Forward to EEP6 |

Annex 6 -  Action Items

Action Items for the IALA Secretariat

- The Secretariat was asked to provide information to EEP Members on or before EEP6 on the process for obtaining copies of the IALA Risk Assessment Tool.	5

- The Secretariat was asked to highlight the concerns of the committee to the Council with regards to developments in synthetic moorings, including the possibility to review and amend the existing guideline on synthetic moorings in the near future.	6

- The Secretariat was asked to bring the review of existing guidelines on synthetic moorings to Council as an additional work item as per IALA Rules of Procedure.	6

- The Secretariat was asked to post the Draft Guidelines on Battery Handling and Maintenance (EEP5/6c/1) as revised, to the Committee Web site by 15 Jan. 05.	7

- The Secretariat was asked to forward the draft IALA Guideline on Solar Sizing (EEP5/output/10) to Council for approval.	7

- Secretariat was requested to submit the IALA Guide To Availability And Reliability Theory And Examples (EEP5/output/06) to Council for approval.	8

- Secretariat was requested to forward the proposed revisions to the ‘Draft Recommendation on Availability Objectives of Aids to Navigation Services’ (EEP5/output/03) to ANM5.	8

- Secretariat was requested to submit the ‘IALA Guidelines for Data Collection for AtoN Performance Calculation’ (EEP5/output/07) to Council for approval.	8

- Preparation of Guidelines on AtoN Training was deferred pending the Training Workshop planned for the Shanghai conference in 2006.	8

- Secretariat was requested to forward the draft list of the required IALA Certification templates covering the full range of AtoN equipment (EEP5/WG2/WP5) to EEP6.	9

- The Secretariat was asked to provide guidance on  the purpose and status of the Certification Templates, as well as how the Templates will be used in the Certification Process, as outlined in EEP5/WG2/WP6, for EEP6.	9

- The Secretariat was asked to forward the liaison note regarding a specification template for self-contained Solar PV Lanterns ( EEP5/output/08) to ANM5.	9

- The Secretariat was asked to forward the Guidelines on environmental considerations in AtoN engineering (EEP5/output/04) to Council for approval.	10

- The Secretariat was asked to forward the updated section 6.2 of the NAVGUIDE (EEP5/output/05) to the ANM5 Committee as per their request.	10

- Secretariat was asked to forward EEP4/6j/1, referring to the development of computer methods and applications, to EEP6.	10

- The Secretariat was asked to forward the IALA Guide To Ambient Light Levels At Which AtoN Lights Should Switch On And Off, EEP5/output/09, to Council for approval.	11

- The Secretariat was requested to submit liaison note EEP5/output/14 to ANM5, requesting updating of the Navguide in line with the Guidelines on Ambient Light Levels At Which AtoN Lights Should Switch On And Off, if the Guidelines are approved by Council.	11

- The Secretariat was requested to forward the IALA Guidelines on Sectors Lights, EEP5/output/12, to Council for approval.	11

- The Secretariat was requested to forward the draft response to the question from Peru (EEP5/output/13) to ANM5 for a response to the third question and then prepare the reply to the Peruvian Hydrographic Office.	11

- The Secretariat was asked to forward the chapter on managing the consequences of technical change – Chapter 7 (EEP5/WG5/WP1) to EEP6.	13

- The Secretariat was asked to provide a report to EEP 6 on the results of the trials on the interactive template for the IALA web site portal relating to historic lighthouses for public relations purposes.	13

- The Secretariat was asked to forward the chapter on Do’s and Don’ts of Preservation of Historic Lighthouses – Chapter 9 (EEP5/6q/1) to EEP6.	13

- Secretariat was asked to forward the draft template on a Methodology for Case Study Evaluation (EEP5/WG5/WP3) to EEP 6	14

- Secretariat was asked to include documents relating to the Wicklow Head Lighthouse and Hook Head Lighthouse visits in the final report for EEP 5.	14

- The Secretariat was asked to format the draft response to John Hopkins (EEP5/output/02) and forward to Mr Hopkins, by October 21, 2004.	14

- The Secretariat was asked to post the results presentation of the Dublin Observation (LED and incandescent lights) to the IALA Committee web site.	15

Action Items for Members

- The Secretariat was asked to forward the Draft Guidelines on Maintenance of Buoys and Small ATON Structures” (EEP5/output/11)to Council for approval.	6

- G. Cunty and M. Wadell were asked to modify the Draft Guidelines on Battery Handling and Maintenance (EEP5/6c/1)  to incorporate the information on the new battery technology identified at IALABATT/IALALITE 5, and forward the modified document to the WG1 Chairman by 10 Dec 04.	7

- The Chairman, WG1, A. Wilkins was asked to finalize the Draft Guidelines on Battery Handling and Maintenance (EEP5/6c/1) as received from G. Cunty and M. Wadell  and forward it to the Secretariat for posting on the EEP Committee web site by 1 Jan 05.	7

- The EEP members are asked to review the Draft Guidelines on Battery Handling and Maintenance (EEP5/6c/1) as revised, and provide comments to A. Wilkins by 1 Apr 05.	7

- A. Wilkins and W. Danzik were asked to lead the intersessional effort to develop a draft methodology guideline for cost/benefit analysis of different types of buoys, with input from other interested WG members.  A draft document will be provided to the Secretariat for posting on the EEP Committee web site by 1 Apr 05.	7

- EEP members were asked to review the draft methodology guideline for cost/benefit analysis of different types of buoys and bring any comments to EEP6.	8

- C Baker - Product Template 1 – Lanterns for buoys and light-beacons, including enclosed rotating beacons for EEP6.	9

- C Lagerwall - Product Template 2 – Lighthouse optical systems and components, for use inside lantern houses for EEP6.	9

- A Wilkins - Product Template 3 – Energy sources and related components, including energy generators, energy storage, and regulation or control devices for EEP6.	9

- S Behrens - Product Template 4 – Buoys, buoy moorings, and structures for land use and for offshore for EEP6.	9

- Committee Members were requested to review the draft list of the required IALA Certification templates covering the full range of AtoN equipment (EEP5/WG2/WP5) and identify national and international test standards applicable as input for EEP6.	9

- M Card was requested to prepare the table showing the relationships between IALA documents and a summary of Recommendations and Guidelines currently under review as input to EEP6.	10

- Input papers EEP5/6n/1 and EEP5/6n/2 were noted. The main task under Item 4.3 is to develop guidelines on a method of specifying LED lanterns. It was noted that there is a significant amount of data and papers on the subject of LEDs, including input and output papers of past EEP meetings. P.C. To and Lu Yongqiang were requested to review the available documents and produce a paper summarising the information as an input paper to EEP6. To assist this process the working group drew up an outline structure for the paper, EEP5/WG4/WP5.	11

- P.C. To and Lu Yongqiang were requested to review the available documents and produce a paper summarising available LED information as an input paper to EEP6.	11

- C Baker was asked to review the IALA Recommendations of Light Signals on Aids to Navigation’ December 1977 and update it to comply with the CIE equivalent standard and to coordinate this work with the proposed specialist working group on Colours Of Light Signals, Calculation of the Effective Intensity of Flashed Lights.	12

- The Secretariat was requested to coordinate the setting up of a Specialist Working Group on Colours Of Light Signals, Calculation of the Effective Intensity of Flashed Lights and the Determination of Luminous Intensity in accordance with the terms of reference EEP5/output/15.	12

- C Martinez and V Rinaldi were asked to update E110 and Navguide section 3.4.3 in accordance with the UN SIGNI Recommendation and submit as input to EEP6.	12

- WG5 members were asked to review the chapter on managing the consequences of technical change – Chapter 7 (EEP5/WG5/WP1) for EEP6.	13

- WG5 members were asked to prepare further input to the chapter on Do’s and Don’ts of Preservation of Historic Lighthouses – Chapter 9 (EEP5/6q/1) for EEP6.	13

- The Chairman of EEP was asked to raise the concerns over PHL/EEP merger(as identified in EEP4/WG5/WP1) at the next meeting of the PAP and report back at EEP 6.	14

- WG5 members were asked to prepare further input to the document Methodology for Case Study Evaluation (EEP5/WG5/WP3) for EEP6.	14

- Members were asked to note the deadline for submissions of abstracts for papers for the IALA 2006 Shanghai Conference.	14

- Members were asked to consider work program items for the work term 2006-2010 for input to EEP6.	15

- The Italian Lighthouse Authority was asked to invite a member of the Department of Cultural and Artistic Goods to describe the work being done in the area of lighthouse preservation and restoration.	58

Annex 7 – Detailed Work programme

(as updated at EEP5)

WG1 – Fixed & floating support structures and power systems - Chairman: A. Wilkins

| Item no. | Original Task no. | Title | Objectives | Work to be undertaken | Work Sessions | Expected completion | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1 | 2 | Develop Guidelines on maintenance practices for buoys and small fixed Aids to Navigation structures, including signal equipment | - Identify and share information on cost effective maintenance practices, new processes and new materials - Produce guidelines | - Use expertise within the committee to identify relevant areas and produce a questionnaire to identify world wide practices that may be incorporated in the final guideline. - Collate the results of the questionnaire into individual topic reports. - Design, write and edit the final guide. | 6 | EEP6 Completed EEP5 |  |
| 1.2 (also refer to 5.1.4) | 8 | Develop Guidelines on the technical aspects of the maintenance of lighthouses | - Divide structures into groups such as construction materials, sites and navigational use - Further divide into historic and maintenance considerations. | - In conjunction with WG5 (not relevant anymore as discussed at EEP2): - Identify areas of expertise required to produce guidelines - Define objectives for a workshop to produce specific sections of the guidelines (not relevant anymore) - Prepare workshop. (See Task 12) (not relevant anymore) - Forward Prepare draft guidelines resulting from workshop and committee input to Council for approval. - Monitor the progress made by the USA Parks in updating their services handbook, with the intention to make a final decision as to the practicality of producing an IALA Guideline in this regard as well. | 4 | Completed at EEP4 |  |

WG1 – Fixed & floating support structures and power systems - Chairman: A. Wilkins

| Item no. | Original Task no. | Title | Objectives | Work to be undertaken |  | Work Sessions | Expected completion | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.3 | M4 | Monitor developments in renewable energy sources. | - Assess new developments, potential applications and the cost effective use of renewable energy sources. - Update relevant Guidelines. | - Monitor, collect and collate information on new developments, potential applications and the cost effective use of renewable energy sources, particularly: - Fuel cells - Wind & Wave Generators - Solar photovoltaic - Report on technical information as it becomes available | Ongoing |  | Report to full committee through rapporteur process. |  |
| 1.4 | M2 | Monitor developments in AtoN support structures and other equipment, excluding light and colour | - Assess potential applications and the cost effective use of new AtoN equipment | - Collect and collate information on new AtoN equipment particularly: - Report on as technical information becomes available |  | Ongoing – report to full committee through rapporteur process. |  |  |
| 1.5 | 15 (Council Report Session 27) | Revise Guidelines on battery handling and maintenance | - Integrate existing guidelines on: - the safe handling of batteries, and - maintenance and Operation of Batteries | - Carry out Intersessional work to create draft of integrated guideline. - Review of draft guideline at EEP2. |  | 3 | Originally estimated to be completed at EEP3, extended to EEP6 |  |

WG1 – Fixed & floating support structures and power systems - Chairman: A. Wilkins

| Item no. | Original Task no. | Title | Objectives | Work to be undertaken | Work Sessions | Expected completion | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1.6 | 16 Carry forward from ENG 16 | Provide guidance on the practicability of a universal IALA Solar Design program based on functional specification | - Review examples of basic solar sizing programs - Determine practicality of creating a universal Solar Design Computer Program - Create a universal Solar Design Computer Program (if feasible) | - Ask all members to bring examples of basic solar sizing programs to EEP2. - Review feasibility of program at EEP2 and determine if work will proceed. | 3 | EEP4 EEP5 for approval Completed EEP5 |  |
| 1.7 |  | Develop subject matter for a workshop in conjunction with WG 5 – refer to item 6 in this regard (not relevant to WG1 anymore) |  |  |  |  |  |
| 1.8 | N/A | Other items as they may arise |  |  |  |  |  |
| 1.8.1 | N/A | Consider and prepare reply re. inquiry from Chilean Lighthouse Service articulated buoys |  |  | 1 | Completed at EEP1 |  |
| 1.8.2 | N/A | Consider and prepare reply re. Inquiry from MENAS on pitting of buoy bodies |  |  | 1 | Completed at EEP2 |  |
| 1.8.3 | N/A | Consider and provide information to the German Authority members on solar superstructures for light buoys (re. EEP2/10/2) |  |  | 1 | Completed at EEP2 |  |
| 1.8.4 | N/A | Consider and prepare reply re. inquiry from “Azim” on aluminium buoys( re. EEP2/10/2) |  |  | 1 | Completed at EEP2 |  |
| 1.8.5 | N/A | Review and update chapter 7 of the Navguide relating to power systems |  |  | 2 | Completed at EEP4 |  |
| 1.8.6 | N/A | Consider and prepare reply re. inquiry from J. E. Ruck on Timeball ( re. EEP3/10/1) |  |  | 1 | Completed at EEP3 |  |
| 1.8.7 | N/A | Consider liaison note from ANM Committee on the marking of wind farms, using AIS |  |  | 1 | Completed at EEP3 |  |
| 1.8.8 | N/A | Prepare Guidelines on the methodology for cost benefit analysis of different types of buoys, if time permits |  |  | 3 | EEP7 |  |

WG1 – Fixed & floating support structures and power systems - Chairman: A. Wilkins

- Sessions

| Item | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1 | ■ | ■ | ■ | ■ | ■ | ■ |  | Completed at EEP5 |
| 1.2 |  |  |  | ■ | ■ | ■ | ■ | Completed at EEP4 |
| 1.3 |  |  |  |  |  |  |  | Monitor Item - ongoing |
| 1.4 |  |  |  |  |  |  |  | Monitor Item - ongoing |
| 1.5 | ■ | ■ | ■ | ■ | ■ | ■ |  |  |
| 1.6 | ■ | ■ | ■ | ■ |  |  |  | Completed at EEP5 |
| 1.7 | ■ | ■ | ■ |  |  |  |  | Not relevant to WG1anymore |
| 1.8.1 | ■ |  |  |  |  |  |  | Completed at EEP1 |
| 1.8.2 |  | ■ |  |  |  |  |  | Completed at EEP2 |
| 1.8.3 |  | ■ |  |  |  |  |  | Completed at EEP2 |
| 1.8.4 |  | ■ |  |  |  |  |  | Completed at EEP2 |
| 1.8.5 |  |  | ■ | ■ |  |  |  | Completed at EEP4 |
| 1.8.6 |  |  | ■ |  |  |  |  | Completed at EEP3 |
| 1.8.7 |  |  | ■ |  |  |  |  | Completed at EEP3 |
| 1.8.8 |  |  |  |  | ■ | ■ | ■ |  |

WG2 – Quality Assurance, Availability and Certification - Chairman: C. Baker

| Item no. | Original Task no. | Title | Objectives | Work to be undertaken | Work Sessions | Expected completion | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2.1 | 6 | Revise Guidelines on Quality Assurance, Availability of systems and components | Provide the membership with up to date information on Quality Assurance, Availability and Reliability issues pertaining to AtoN systems and components. Maintain present Guidelines in an updated condition, taking into consideration new techniques being developed by member Authorities and the International community Continue making member Authority’s specifications available. Obtain information on member’s testing and performance measuring facilities with the intention of facilitating co-operation | Revise IALA Guide to the availability and reliability of aids to navigation Review and produce relevant documentation on availability and reliability techniques, objectives, levels and related issues Prepare specification templates for aids to navigation systems and components. Arrange a questionnaire to determine the testing and performance measuring facilities of Members and compile a database to be linked to the IALA web site. Produce articles for the IALA bulletin on this subject | 4 | EEP4 EEP5 Completed at EEP5 |  |

WG2 – Quality Assurance, Availability and Certification - Chairman: C. Baker

| Item no. |  | Original Task no. | Title | Objectives | Work to be undertaken | Work Sessions | Expected completion | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2.2 |  | 7 | Develop Guidelines on the Methodology of collecting information on reliability and failures of AtoN equipment | - Provide the membership with up to date information on how to collect information on reliability and failures of AtoN equipment | - Draft Guidelines making keeping in mind ENG16/8/10, using Trinity House document as a template. | 4 | EEP7 EEP5 Completed at EEP5 |  |
| 2.3 |  | M5 | Monitor the development of the IALA equipment certification process | - Contribute towards Equipment Certification as and when required | - Contribute towards Equipment Certification as required. - Prepare product specification templates. | Ongoing / to be actioned | EEP5 / 6 / 7 |  |
| 2.4 |  | 13 (2002 IALA Conference Recommen-dations) | Revise the guidelines on AtoN Training | - Maintain and update the IALA Guidelines on AtoN Training. | - Utilise the expertise within the Committee to review each part of the guidelines - Workshop to be arranged to produce detailed guidance on developing AtoN Training Modules | Deferred – Shanghai Conference AtoN Training Workshop | deferred |  |
| 2.5 | N/A |  | Other items as they may arise |  |  |  |  |  |
| 2.5.1 | N/A |  | Provide comments as requested by the AIS Committee on the Preliminary Draft Recommendation – AIS for Aids to Navigation |  |  | 1 | Completed at EEP2 |  |
| 2.5.2 | N/A |  | Consider and provide comments as requested by the AIS Committee on the MMSI Number Assignment for Synthetic AIS and Virtual AtoN ais |  |  | 1 | Completed at EEP2 |  |
| 2.5.3 | N/A |  | Provide a sample certification template as requested by Secretariat |  |  | 1 | Completed at EEP2 |  |
| 2.5.4 | 2.3 |  | Produce additional certification templates |  |  | 3 | EEP7 |  |

WG2 – Quality Assurance, Availability and Certification - Chairman: C. Baker

- Sessions

| Item | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2.1 | ■ | ■ | ■ | ■ | ■ |  |  | Completed at EEP5 |
| 2.2 |  | ■ | ■ | ■ | ■ | ■ |  | Completed at EEP5 |
| 2.3 | ■ | ■ | ■ | ■ | ■ | ■ | ■ | Ongoing |
| 2.4 |  | ■ |  |  |  | ■ | ■ | Deferred EEP4 – Shanghai AtoN Workshop, 2006 |
| 2.5.1 |  | ■ |  |  |  |  |  | Completed at EEP2 |
| 2.5.2 |  | ■ |  |  |  |  |  | Completed at EEP2 |
| 2.5.3 |  | ■ |  |  |  |  |  | Completed at EEP2 |
| 2.5.4 |  |  |  |  | ■ | ■ | ■ |  |

WG 3 - Environment And Publications Chairman – R. Beauchesne

| Item no. | Original Task no. | Title | Objectives | Work to be undertaken | Work Sessions | Expected completion | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.1 | 1 | Develop Guidelines on environmental considerations on AtoN engineering | - To raise the profile of environmental issues in the AtoN community - To produce a “Green Guide” to AtoN operation, including how to dispose of batteries and other hazardous material | - Design and circulate a questionnaire on local legislation and environmental considerations - Collate questionnaire responses - Design, write and edit Guides | 7 | EEP7 Completed at EEP5 |  |
| 3.2 | 5 | Review and update relevant sections of the NAVGUIDE | - To keep the NAVGUIDE updated on engineering issues. - Keep relevant documentation under review and update as and when required, e.g. dictionaries | - Review all relevant NAVGUIDE chapters from an Engineering Committee’s perspective and produce any new and/or revised text for inclusion in the next version of the NAVGUIDE: - Review relevant documentation and update where necessary | 4 | EEP4 |  |
| 3.3 | M1 | Monitor the development of computer methods and applications to simplify design and management of AtoN | - To identify computer programmes and methods used by AtoN operators - To make this information available to the IALA membership | - An annual questionnaire will be circulated to the membership; the information will be collated annually culminating in: - Produce a report and circulate it before the next Conference - Monitor availability of new computer programmes | Ongoing | Report to full committee through rapporteur process. |  |

WG 3 - Environment And Publications Chairman – R. Beauchesne

| Item no. |  | Original Task no. | Title | Objectives | Work to be undertaken | Work Sessions | Expected completion | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3.4 | N/A |  | Other items as they may arise |  |  |  |  |  |

Sessions

| Item | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3.1 | ■ | ■ | ■ | ■ | ■ | ■ | ■ | Completed at EEP5 |
| 3.2 | ■ | ■ | ■ | ■ | ■ |  |  |  |
| 3.3 | ■ | ■ | ■ | ■ | ■ | ■ | ■ | Ongoing |
| 3.4 | ■ | ■ | ■ | ■ | ■ | ■ | ■ | N/A |

WG 4 - Light and colour – Chairman – S. Doyle

| Item no. | Original Task no. | Title | Objectives | Work to be undertaken | Work Sessions | Expected completion | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 4.1 | 3 | Develop Guidelines on ambient light levels at which AtoN lights should switch on and off | - Produce a definitive Guideline on this subject | - Obtain standards developed by Lighthouse Authorities - Obtain the opinion of technical experts - Achieve consensus within the Committee - Design, write & edit Guide | 4 | EEP5 EEP 6 Completed at EEP5 |  |
| 4.2 | 4 | Develop Guidelines on sectors, sector lights and sector projection lights | - Provide information on the different types of sector projectors, their advantages and disadvantages, equipment availability and guidance on installation - Produce Guidelines | - Collate information on commercial sector projectors - Obtain specialist information on incorporating sectors in lanterns and fixed lenses - Edit information - Design, write and edit Guide | 4 | EEP6 Completed at EEP5 |  |
| 4.3 | 14 (2002 IALA Conference Recommen-dations) | Study the spectral and spatial characteristics of new and developing new lights, in particular LED’s with the view of informing the IALA Membership and to update relevant IALA documentation | - Provide the Committee and the membership with relevant and updated information on this topic - Develop a Guideline on a method for specifying LED lanterns, taking into account vertical and horizontal divergence. | - Study the operating characteristics of LEDs and other light sources, including the vertical divergence and the variance in angular intensity, when used as AtoN light sources - When appropriate, review applicable IALA Recommendations and Guidelines - Write articles for the IALA bulletin on the subject | 6 | EEP7 |  |

WG 4 - Light and colour – Chairman – S. Doyle

| Item no. | Original Task no. | Title |  | Objectives | Work to be undertaken | Work Sessions | Expected completion | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 4.4 | M3 | Monitor international progress on colours of light signals, calculations of the effective intensity of flashed lights and the determination of luminous intensity |  | - Ability to update IALA Recommendations in these areas - Update relevant IALA Recommendations and standards - Address Blue Light as required and incorporate in relevant Recommendations and Guidelines | - Create a specialist Working Group - Liase with relevant technical specialists and international committees - Use the information to design, write & edit new recommendations and standards to supersede, or review and update current, if need be: - Recommendation for the Calculation of Effective Intensity (1980) - Recommendations for Colours of Light Signals - Recommendation on Luminous Intensity - Recommendation on Photometry | Ongoing | Report to full committee through rapporteur process. Complete specialist working group at EEP7 |  |
| 4.5 | M2 |  | Monitor developments in AtoN | - Access potential applications and the cost effective use of new visual AtoN equipment - Write a report or guide on each new type of equipment | - Collect and collate information on new visual AtoN equipment particularly: - The use of low power directly projected Laser leading lights - The operating characteristics of LED’s when used as AtoN light sources - Maintain and update as necessary the “Guidelines on new Light Sources and associated Power Supplies“ - Report as technical information becomes available | Ongoing | Report to full committee through rapporteur process. |  |

WG 4 - Light and colour – Chairman – S. Doyle

| Item no. |  | Original Task no. | Title | Objectives | Work to be undertaken | Work Sessions | Expected completion | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 4.6 | N/A |  | Other items as they may arise |  |  |  |  |  |
| 4.6.1 | N/A |  | Consider and prepare reply re. inquiry from Fisheries and Ocean, Canada re. Leading Light Designs |  |  | 1 | Completed at EEP2 |  |
| 4.6.2 | N/A |  | Review recommendation E108 on Surface colours used for Visual Signal Aids to Navigation, to ensure it reflects relevant CIE and IALA documents. Update recommendation if needed. |  |  | 3 | EEP5 Completed at EEP4 |  |
| 4.6.3 | N/A |  | Revise Section 3.7 of the IALA Navguide relating to Sector Light and Leading Range Lights. |  |  | 2 | Completed at EEP4 |  |
| 4.6.4 | N/A |  | Revise Section 3.3.3 and Section 3.4 of the Navguide while implementing comments from Japan EEP4/6i/4 |  |  | 1 | Completed at EEP4 |  |
| 4.6.5 | N/A |  | Add graphical representation and numerical examples of light characters to Chapter 3 of the Navguide, taking account of EEP4/2/2 |  |  | 2 | EEP6 |  |
| 4.6.6 | N/A |  | Respond to query from Peruvian Hydrographical office regarding LED’s Lighthouse categorization and hazard marking |  |  | 1 | Completed at EEP5 |  |
| 4.6.7 | N/A |  | Respond to IALABATT recommendation no. 9. Develop guidance on the use of modern light sources, such as clusters of lamps or LED’s or single high power LED’s in traditional optics, time permitting. |  |  | 2 | EEP7 |  |

Sessions

| Item | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 4.1 | ■ |  | ■ | ■ | ■ |  |  | Completed at EEP5 |
| 4.2 |  |  | ■ | ■ | ■ | ■ |  | Completed at EEP5 |
| 4.3 |  | ■ | ■ | ■ | ■ | ■ | ■ |  |
| 4.4 | ■ | ■ | ■ | ■ | ■ | ■ | ■ |  |
| 4.5 |  | ■ | ■ | ■ | ■ | ■ | ■ |  |
| 4.6.1 |  | ■ |  |  |  |  |  | Completed at EEP2 |
| 4.6.2 |  |  | ■ | ■ | ■ |  |  | Completed at EEP4 |
| 4.6.3 |  |  | ■ | ■ |  |  |  | Completed at EEP4 |
| 4.6.4 |  |  |  | ■ |  |  |  | Completed at EEP4 |
| 4.6.5 |  |  |  |  | ■ | ■ |  |  |
| 4.6.6 |  |  |  |  | ■ |  |  | Completed at EEP5 |
| 4.6.7 |  |  |  |  |  | ■ | ■ |  |

WG 5 - Preservation Of Historic Lighthouses and AtoN - Chairman: L. Wilson

| Item no. | Original Task no. | Title | Objectives | Work to be undertaken | Work Sessions | Expected completion | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 5.1 | Further develop Preservation Manual to include chapters on: |  |  |  |  |  |  |
| 5.1.1 | 9 | Funding options for the preservation of historic lighthouses | - Provide guidance on how to assess opportunities to obtain funding for the preservation and maintenance of historic lighthouses | - Design, edit and produce guidance - Review existing Preservation Manual and include new chapter - Issue updated edition of the Guide | 4 | Completed at EEP3 |  |
| 5.1.2 | 10 | Means to record and document changes in the history of lighthouses | - Indicate the importance of the documentation of lighthouse history and to give guidance on: - Where existing documentation is to be found - How to record the development of changes in lighthouse history - How documentation should be managed. | - Design, issue and review questionnaire on retention and control of historic documentation - Design, edit and produce guidelines on documentation of lighthouse history - Review existing manual to incorporate chapter on documentation of lighthouse history | 5 | EEP6 Work Completed at EEP4 |  |

WG 5 - Preservation Of Historic Lighthouses and AtoN - Chairman: L. Wilson

| Item no. | Original Task no. | Title | Objectives | Work to be undertaken | Work Sessions | Expected completion | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 5.1.3 | 11 | Managing the consequences of technical changes | - Provide guidance to authorities on how to manage the introduction of new AtoN technology while preserving the historic lighthouse. | - Design, edit and produce guidelines on the introduction of new AtoN while preserving historic lighthouse - Review existing manual to incorporate a chapter on the introduction of new AtoN while preserving historic lighthouse - Review technical options and their implications to historic lighthouse preservation. | 5 | EEP6 |  |
| 5.1.4 (also refer to 1.2) | 8 | Technical aspects of the maintenance of historic lighthouses in conjunction with WG1. | - Refer to 1.2 | - Refer to 1.2 |  | Completed |  |
| 5.1.5 |  | Lessons learned in the preservation of historic lighthouses |  | Incorporate chapter on the do’s and don’ts of preservation of historic lighthouses | 4 | EEP6 |  |
| 5.2 | 12 | Develop an IALA web site portal relating to historic lighthouses for public relations purposes | - Encourage public awareness by initiating a facility enabling member countries to display information on their historic lighthouses | - Review previous work and interface with new IALA website - Carry out interactive template trials - Promote member country participation in recording data | 5 | EEP7 |  |
| 5.3 |  | Develop subject matter for a Workshop in conjunction with WG 1 – refer to item |  |  |  | Not relevant to WG5 anymore, following EEP2. |  |

WG 5 - Preservation Of Historic Lighthouses and AtoN - Chairman: L. Wilson

| Item no. |  | Original Task no. | Title | Objectives | Work to be undertaken | Work Sessions | Expected completion | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5.4 | N/A |  | Other items as they may arise |  |  |  |  |  |
| 5.4.1 | N/A |  | Develop subject matter for a possible seminar on the practical aspects of lighthouse preservation. |  |  | 3 | Completed at EEP4 |  |
| 5.4.2 | N/A |  | Respond to query from Hopkins and Associates Preservation Consultants regarding history of Fresnel lenses particularly of Sautter Paris. |  |  | 1 | Completed at EEP5 |  |
| 5.4.3 | N/A |  | Develop a template for methodology for case study evaluation. |  |  | 2 | EEP6 |  |

Sessions

| Item | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5.1.1 | ■ | ■ | ■ | ■ |  |  |  | Completed at EEP3 |
| 5.1.2 | ■ | ■ | ■ | ■ | ■ | ■ |  | Completed at EEP4 |
| 5.1.3 | ■ | ■ | ■ | ■ |  | ■ |  |  |
| 5.1.4 | Refer to 1.2 |  |  |  |  |  |  | Complete |
| 5.1.5 |  |  | ■ | ■ | ■ | ■ |  |  |
| 5.2 | ■ | ■ | ■ | ■ |  |  | ■ |  |
| 5.4.1 |  |  | ■ | ■ | ■ |  |  | Completed at EEP4 |
| 5.4.2 |  |  |  |  | ■ |  |  | Completed at EEP5 |
| 5.4.3 |  |  |  |  | ■ | ■ |  |  |

6 - Prepare and convene a Workshop/Seminar

| Item no. | Original Task no. | Work to be undertaken | Expected completion | Comments |
| --- | --- | --- | --- | --- |
| 6.1 |  | Develop subject matter, objectives and title of proposed Seminar on the preservation of historic lighthouses - Refer to 5.4.1 in this regard | Completed at EEP4 |  |
| 6.2 |  | Comment on the proposal of an IALABAT/LITES Workshop received from the Industrial Members (WG1 & WG4) | Completed at EEP3 |  |
| 6.3 |  | Develop subject matter, objectives and title of proposed AtoN Training Workshop - Refer to 2.4 in this regard | Completed at EEP3 |  |

EEP 1 – October 2002 EEP 4 – April 2004 EEP 6 – April 2005 EEP 2 – April 2003 EEP 5 - October 2004 EEP 7 – October 2005 EEP 3 – October 2003

Each WG is requested to consider all the above mentioned tasks and:

- If necessary, produce a summary of the WG’s understanding of the assignment(s), to assist all members to have a clear understanding thereof.  This can also be used as a future Terms of Reference (TOR) for the assignment.

- Prioritise the tasks

- Confirm the end results

- Review work programme and confirm the target dates

- Provide an action plan to meet the end results and target dates

- Produce report and working papers for discussion in the plenary sessions

Annex 8 - IALA Committee Provisional Agenda EEP6

| EEP Committee 6th session Agenda item 1 | EEP6/1/1 |
| --- | --- |

The 6th meeting of the EEP Committee will be held from April 4-8, 2005 at IALA Headquarters, Saint Germain en Laye, France. The opening plenary will commence at 1300 on Monday, April 4 and the closing plenary will end at approximately 1300 on Friday, April 8.  Committee Chair, Vice-chair and working group Chairpersons are requested to meet at 1000 on Monday April 4, 2004.

## AGENDA

- Approval of the agenda.

- Review of action items from EEP5.

- Review of input papers.

- Reports from other bodies:

4.1	IALA Council

4.2	IMO

4.3	Other input as appropriate

- Report from Rapporteurs for items to be monitored

5.1	Developments in AtoN (Item 1.4 and 4.5, M2);

5.2	International progress on colours of light signals, calculations of the effective intensity of flashing lights and determination of luminous intensity (Item 4.4, M3);

5.3	Development on renewable energy sources (Item 1.3, M4).

5.4	Development of the IALA equipment certification process (Item 2.3, M5).

- Work Programme

- Work Programme related Items

- Revise Guidelines on Battery Handling and Maintenance (Item 1.5, Task 15*).

- Prepare guidelines on the methodology for cost benefit analysis of different types of buoys (Item 1.8.8 as approved by Council Session 34)

- Revise Guidelines on Quality Assurance, Availability of systems and components (Item 2.1, Task 6*).

- Develop Product Certification Templates (Item 2.3, Task M5 refers – as requested by Council Session 33 / 34).

- Produce additional certification templates (Item 2.5.4).

- Review and Update Relevant Sections of the Navguide (Item 3.2, Task 5*).

- Provide a report on the availability of computer methods and applications to simplify design and management of AtoN (Item 3.3, Task M1*);

- Study the Spectral and Spatial Characteristics of New and Developing New Lights (Item 4.3, Task 14*).

- Add graphical representation and numerical examples of light characters to Chapter 3 of the Navguide (Item 4.6.5).

- Respond to IALABATT recommendation no. 9. Develop guidance on the use of modern light sources, such as clusters of lamps or LED’s or single high power LED’s in traditional optics, time permitting. (Item 4.6.7 – pending council approval)

- Develop Chapter on managing the consequences of Technical Changes (Item 5.1.3, Task 11*).

- Develop Chapter on experiences gained - Do’s and don’ts of Preservation of AtoN (Item 5.1.5).

- Develop an IALA web site portal relating to historic lighthouses for public relations purposes (Item 5.2, Task 12)

- Develop template for methodology for case study evaluation.  (Item 5.4.3)

- Review of output and working papers.

- Any other business.

- Review of session report.

Members are requested to provide comments or proposals on any of the above items to the Secretariat by not later than March 4, 2005.

Documents received by the Secretariat will be published on the Committee web-site normally within three working days of receipt.

Note – items marked with an asterix (*) reflect the Task Number referenced in the Proposed Work Programme as approved by IALA Council.

Annex 9 – Developments in Lighthouse Preservation / Technical Visit Information

A key objective of WG5 is the sharing of information in regards to Lighthouse Preservation initiatives within member countries.  The following is a summary report provided at EEP4.

### Belgium

### The Belgian Coast is 67 km long and has four harbours each with their own lighthouses. From west to east, Nieuwpoort has a concrete tower, operational; the keeper’s house is restored as a wildlife watch house. Ostend has a 65 m concrete tower, operational and was restored purely for stability reasons in 1995. Blankenberge has a concrete tower, operational; the keeper’s house is restored as a shed for the rescue service and partly as a maritime museum. Zeebrugge has a concrete tower, without keeper’s house; restored and repainted , not operational.

### Canada

The Canadian Coast Guard continues to move towards lighthouse divestiture and de-staffing where it is possible to do so.

Currently only two regions in the country have significant numbers of staffed lighthouses, Pacific Region and Newfoundland Region, a total of approximately 50 remain.

A strategic plan is under development for a National Lighthouse Divestiture programme, which recognises the significant role of preservation societies and the importance of preserving these structures.

In the meantime a private member’s bill on lighthouse preservation continues to be debated in parliament.

### China

A report was submitted to WG 5 relating to the Chinese Exhibition Centre of Aids to Navigation which has been constructed in the south of the Dongshan Park in Qinhuangdao City.

Note: a copy of this report is attached to this annex.

### England (Trinity House)

Holiday letting is progressing well and level of lettings is higher than expected. “Rural Retreats”, www.ruralretreats.co.uk are running these at 4 new locations at a quality level on behalf of Trinity House. Problem identified when maintenance requires to be planned further ahead and empty space allocated in houses. Attendance figures at 11 visitor centres have further increased during 2004.

Lizard Point stage one lottery grant application submitted and approved. A combination of insufficient funding available from Lottery Fund and a requirement to rewrite the business plan has delayed the project.

### France

#### Since April 2004, National Preservation Plan for our 150 "historic lighthouses" had not made any progress.

40% of these 150 lighthouses are still manned and 50% of these are opened to the public mainly with free entrance under the guidance of the keeper.

### Italy

The Italian Lighthouse Authority informed IALA that a project for preservation and restoration of lighthouses started in 2003 by the Department of Cultural and Artistic Goods (which is an agency of the environment).   The Italian Lighthouse Authority suggested that a member of the Department of Cultural and Artistic Goods (which is an agency of the environment) be invited to attend EEP 6/WG 5 in order to describe the work being done in the area of lighthouse preservation and restoration.

Action Item

The Italian Lighthouse Authority was asked to invite a member of the Department of Cultural and Artistic Goods to describe the work being done in the area of lighthouse preservation and restoration.

It should be noted that WG 5 appreciates the attendance of a representative from Italy and look forward to their attendance at EEP 6.

### Norway

The representative from Norway was unable to attend. However an update of the Nortrail Project has been provided.

In addition a copy of the co-operation agreement relating to the European Commission funding of a restoration and preservation strategy for European Masonry Lighthouses – PHAROS. The universities of Thessalonikis, Barcelona, De Montfort-Leicester and Cyprus Port Authority as well as the Cultural Heritage Directorate of Norway are involved

Note: attached is the update on the Nortrail Project and the Co-operation Agreement.

### Scotland - including update on Lighthouse Project – Interreg IIIB Atlantic Coast Programme

In Scotland two lighthouses, Mull of Galloway and North Ronaldsay, have been open to the public for a third season and this year we have established an arrangement with the local trust at Ardnamurchan to open our third lighthouse. This has now been achieved and the lighthouse has been open to the public with guided tours every day to suit demand. During the last three months many people have therefore been able to see the tremendous views of the area, generally for the first time since the keepers left in 1986.

We have 4 holiday cottages available to general public at 3 sites through National Trust for Scotland and are about to modernise at a further three sites although unfortunately this will include the those formerly utilised for staff letting.

Other important projects at planning stage are the refurbishment and modernisation of Mull of Galloway Lighthouse with an application for a Historic Building Repair grant to be submitted and a proposal has been submitted for the relighting of a listed lighthouse tower on the Monach Isles, which was abandoned in 1942.

As previously mentioned The Northern Lighthouse Board is currently participating in a European project called the Atlantic Coast Project. The objective of the project is the regeneration of valuable architectural and cultural heritage lighthouses, along the coastline of the different regions involved. The project aims to study the viability and implementation process of suitable alternative uses for the lighthouses, that could be of cultural, social, tourist or business interests, taking into consideration aspects such as accessibility, visitors safety, visibility and environmental impact. It will also allow the production of relevant promotional materials and the implementation of joint promotional campaigns.

In September Northern Lighthouse board hosted a second managing committee meeting in Edinburgh where the different members provided progress reports. Members were present from City Councils of Bayona (Galicia), Cudillero (Asturias), Gijon (Asturias), Llanes (Asturias), Ribadesella (Asturias) and San Vicente de la Barquera (Cantabria) - Spain, Canary Islands, Northern Lighthouse Board - Scotland, Trinity House - England & Wales, Syndicat des Caps, Frehel -France and South West Ireland Regional Authority, Ireland.

During the meeting the discussions covered progress in the production of a standard logo, which was provided at the meeting to allow all members to produce publicity material incorporating the logo. In addition NLB has developed proposals to install public information signs at 20 lighthouses including those open to the public as well as providing webcam cameras to allow disabled people and others to see the view from the lighthouse balcony. A proposal has been agreed for a photographer from Asturias to travel to each of the countries involved to produce a set of photographs in a similar style, which will be available to members for public relations and publicity purposes. The next meeting is to be held in the Canary Islands in February.

In addition the following aims are still included as part of the longer-term future of the project.

- Elaboration of individual and/or common studies on the uses of the lighthouses.

- Elaboration of studies in order to improve the accessibility and security within the lighthouse surroundings and pilot projects implementation.

- Elaboration of common promotional and teaching materials (edited materials, Web pages etc.)

- Joint participation in promotional events (such as tourist or cultural fairs)

- Exchange of experiences and knowledge (study visits, seminars and conferences etc.)

### Spain

The new President of Puertos del Estado, Mariano Navas, is the designer of more than 25 lighthouses and was the first Spanish representative at IALA.  As such it is expected that he will be a good support in preservation initiatives.

Puertos del Estado has made contacts with CEHOPU, the centre specialised in historic studies on public works, and with other bodies interested in preservation and likely to support them. A department of the Spanish Ministry of Agriculture and Fisheries is carrying out restoration projects on some lighthouses. Both these bodies are considering sending representatives to the Lighthouse Preservation Seminar in Gothenburg next year.

The Port Authorities are also very active:

- The Torres Lighthouse project consists of the establishment of a small exhibition as the result of an agreement with the Port Authority and the local community;

- In Barcelona, Monjuitch Lighthouse is being restored and will become the new Headquarters of the Port Authority;

Finally, a book on Mesa Roldan lighthouse in Almeria has been published. The author, a lightkeeper, is preparing another book on lighthouse keepers’ life with a specific chapter on women lighthouse keepers.

### Sweden

The IALA Council has approved the venue for the seminar on Practical Aspects of Lighthouse Preservation. This seminar will take place in Gothenburg August 16 - 19, 2005 and hosted by the Swedish Maritime Administration. A steering Committee Meeting took place August 23 – 28, 2004 in Gothenburg in order to plan and organise the upcoming event.

The Chinese Exhibition Center

Of Aids to Navigation

The short guide to the Exhibition Center of Aids to navigation

The aids to navigation are important facilities used for assisting navigation by keeping water transportation unimpeded and ensuring that the navigation is safe and economical; they play an important role in water transportation, supporting the development of marine resources, fishery, national defense and state sovereignty defense.

The aids to navigation in China enjoy a long history. As early as 4000 years ago, with the upsurge of water transportation, the embryo of aids to navigation emerged. The aids to navigation have a long history of ups and downs, and have grown, from the initial natural aids to navigation, artificial aids to navigation, etc, to the highly automatic aids to navigation at present. Now China has installed over 40000 aids to navigation of all kinds, all these form a comprehensive navigation-assisting system on whole. The development of aids to   navigation does not only ensure the reliable navigation for the ships home and abroad, but also provides favorable conditions for strengthening the ties of trade with other countries in the world and   promoting the development of domestic economic.

For displaying the historical development of the aids to navigation in  China. We have built the Chinese Exhibition Center of Aids to   Navigation. The exhibition center is situated on the south of the beautiful Dongshan park of Qinhuangdao city, its construction area is   1809.22 sq.m. ,the area of the exhibition hall is 949.9 sq.m. , the subsidiary area is 859.32 sq.m.,the exhibition hall has 3 floors.

The exhibition center has 5 exhibition areas, the first exhibition area generally introduces the present condition of the aids to navigation, the second exhibition area dates back to the aids to navigation in ancient times, the third exhibition area displays the condition of the aids to navigation in modern times(1840-1949),the fourth exhibition area displays the development of the present-day aids to navigation from all perspectives, the fifth exhibition area displays some large equipment of the aids to navigation outside.

The first exhibition area and second exhibition area is located on the first floor of the exhibition hall, the third exhibition area is located on the second floor of the exhibition hall, the fourth exhibition area is located on the third floor of the exhibition hall, the fifth exhibition area is an outdoor exhibition area.

What is displayed in the Chinese Exhibition Center of Aids to Navigation is a concentration of thousand-of-year history of the aids to navigation and the diligence and pioneering spirit of generations of the technicians of aids to navigation. All the technicians of aids to navigation are determined to make persistent efforts on their post to ensure the safe navigation of ships and make greater contributions to the socialist construction.

The First Exhibition Area

The First Floor Exhibition Hall

China has a vast territory with spacious sea areas and numerous rivers and lakes, The Coastline is as long as 18,000 Kilometers ,and the total length of rivers is over 430,000 Kilometers .The Chinese aids to navigation went through long years and entered a new stage of overall development They have made remarkable Contributions the safe navigation of ships. This exhibition area mainly displays with charts the management organizations, scope of management, types, quantity and distribution of the aids to navigation in China

The Second Exhibition Area

As early as 4,000 years ago, with the rising of navigation, the aids to navigation in China started their long -standing history of being used in aid of navigation. They went through different stages: from using natural marks to using simple artificial marks, and from building and managing olds to navigation by non-governmental funding to building aids to navigation and appointing people to manage them by governmental funding, This exhibition area, as mainly led in by the great navigator called Zhenghe and his magnificent feat of going on the voyage to the south Pacific Ocean and Indian Ocean seven times, dales back to the aids lo navigation in ancient times, with a display of models, pictures and written materials

The Third Exhibition Area

The Third Floor Exhibition Hall

After the Opium War, some capitalist countries in the west invaded the Chinese coastal areas and the inland rivers. In order to open up the way for plundering , they forced The corrupted Chinese government in Qing Dynasty to sign a series of unequal treaties. Through the customs manipulated by them, they launched an unbridled installation of the aids to navigation in the coastal area, the Yangtze River and the open ports and waterways, hence raised the curtain for the establishment of the aids to navigation in China in modern times. This exhibition area, with historical materials, material objects, models and pictures, displays the conditions of aids to navigation in modern times(1840-1949).

The Fourth Exhibition Area

On October 1,1949, the People’s Republic of China was founded. After the founding of New China, the management system of the aids to navigation in China has experienced great changes several times, and finally developed into the current setup of being superintended by three departments, namely, the Ministry of Communications, the navy and the fishery department, with the Ministry of Communications as the main body. The establishment, management, scientific research, industry and personal training concerning the aids to navigation in present-day China are all growing steadily with the reform on their management system, and are, under the great influence of the reform and Open-day policy, entering a stage of all-round construction of modernization, This exhibition area displays the development of the present-day Chinese aids to navigation from all perspectives

The Fifth Exhibition Area

Note – Cooperation Agreement included as separate, PDF, file.

SEPTEMBER 2004

News from Nave Nortrail on the heritage network ”Lighthouses and maritime communication lines”

NAVE Nortrail aims to organise different heritage networks with the co-operation of a 26 region wide partnership within 7 nations facing the North Sea. The purpose of these networks is to create a place for exchange of experience, to distribute information on mutual interests and discover commonality within the North Sea area.  Hopefully this co-operation could lead to identify different aspects of the same North Sea cultural traditions that each of the participating institutions/organisations is managing and represents through their daily activities, and on this basis strengthen the trans-national co-operation cross the North Sea.  The members of a Nave Nortrail heritage Network will to a large extend define the development of it. But among others, it is supposed to initiate exchange of information and views among participants; it will work to create linkages between places of particular interests in the partner regions and also aim to be a tool in the process of marketing the Nortrail network of pathways.

At the 3rd NAVE Nortrail transnational meeting in Gothenburg January 2004, it was decided that Norway should host the ”Lighthouses and maritime communication lines” heritage network. A working group representing the Norwegian consortium was formed, with Egil Larsen (Rogaland), Jan Aakvik (Møre og Romsdal) and Linn Knudsen (Vest Agder) as members. Together with project officer Jone Engelsvold, this group has taken the responsibility to form a text that should act as an invitation for the NAVE Nortrail partners to join this heritage network. The invitation is attached.

Since the forming of the working group there has been sent out invitations to all Nortrail partners, and all the members are now working on making presentations of themselves that will be on the internett. We have decided to keep focus on issues concerning future use of the lighthouses. And for the next few months we will start working on a pilot project on this theme together with Kystverket in Norway. There has been made a plan for this project and we are going to take it into action during the forthcoming months. The agenda is still not finished or published in english, but it will be available at www.nave.no in short time. The working group will also have a new meeting with Kystverket  in short time. Information on the pilot project will be published on the internett.

Attached are the invitation to the network and the latest newsletter.

Kind regards

Linn Knudsen

(Working group)

International Association of Lighthouse Authorities

Commissioners of Irish Lights

Visit to Hook Heritage Centre and Lighthouse on 3rd October 2004

The Hook Lighthouse is a rare example of an almost intact medieval lighthouse. Dating from the early 13th Century, it represented a major feat of building at the time of its construction. It is of great archaeological , architectural and historical importance. Except for a short break in the 17th Century, this unique tower has served as a lighthouse for 750 years. It is regarded as the oldest lighthouse in Ireland and Great Britain, and it is probably one of the oldest in Europe.

Hook Head Lighthouse was converted to automatic operation in 1996. As a consequence, the lighthouse keepers were permanently withdrawn from the station on 29th March 1996. A further consequence of the automation was that the two dwelling houses at the station were surplus to requirements and an alternative use for these dwellings was sought.

Opening the lighthouse tower to the public was the brainchild of Micheal O’Neill, Irish Lights Commissioner and then Vice Chairman of the Board. He felt that the wonderful history of this tower and a lighthouse keeping throughout the ages should be available to be enjoyed by local people and visitors from throughout Ireland and beyond.

Because of its unique historical and architectural significance the Commissioners took the unusual step of investigating the possibility of developing a partnership arrangement with the local community with the aim of opening the tower to general public. From these initial contacts the company now running the Centre, Hook Heritage Ltd., was formed.

This is a good example of public sector partnership with representatives of Wexford County Council, South East Region Tourist Authority, County Wexford Partnership, representatives of the local community, and the Commissioners of Irish Lights working towards the long term success of the Centre.

In 1999 Hook Heritage signed a lease agreement with Irish Lights whereby the dwellings would be developed into a Visitor Centre including a coffee shop and craft shop. The tower is licensed to Hook Heritage Ltd. To allow them conduct guided tours at particular times during the year.

The Centre is now open all the year round except 15 days around Christmas, and is visited by 65,000 persons a year. Part of the admission fees are returned to the administration of CIL.

Hook Lighthouse Visitor Centre was officially opened by the President of Ireland, Mrs. Mary McAleese on 25th April 2001.

The lighthouse part of the station is manager by the Commissioners f Irish Lights Attendant, Tux Tweedy.

Visit to Wicklow Head Lighthouse and Octagonal Tower

on 6th October 2004

Welcome Address

Ladies and gentlemen, on behalf of the Commissioners of Irish Lights I would like to welcome you all to Wicklow Head Lighthouse, here in County Wicklow.  We are approximately 60 km south of Dublin, on the east coast, in a part of Ireland known as the “garden of Ireland”.  What I would like to do at this point is to briefly outline the historical context of the Wicklow Head lighthouses for your information and explain the background to relationship between the Irish Landmark Trust and Irish Lights in the context of the restoration of the Octagonal tower.

A lighthouse facility has existed here on the head since the late 1700’s.  Originally, two octagonal stone tower lighthouses were built and their lights established in 1781.  They not only marked the headland but prevented mariners from confusing Wicklow Head with Howth and Hook Head, both of which had single lights.  The light source in each lantern was twenty tallow candles.  In fact, Wicklow Head was the last light lit by candles.  Around 1801, consideration was given to rebuilding the Wicklow Head lights at a lower level due to the fact that the rear light was liable to be obscured by fog.

Two new lighthouse towers, fitted with Argand oil lamps, were established in 1818 to a design by George Halpin on the same bearing as the 1781 towers, with the new upper lighthouse close to the old front tower and the new front lighthouse tower further down the cliff.  The 1781 front tower was completely demolished and at the same time the rear light was discontinued but the tower remained, forming a useful landmark by day.

On the night of 10th October 1836 lightning struck the old rear tower and in the ensuing fire the lantern and all floors were completely gutted.  Because the tower formed a useful landmark by day, a recommendation was made that it should be re-roofed but it was not until 1866 that the present brick dome was added.  This rear tower still stands here today minus its lantern but with the brick protecting dome that was added in 1866.

In June 1865 a new lightvessel, known as the Wicklow Swash, was established off the Head and the rear light was discontinued.  Coinciding with the discontinuance of the rear light, the lower light was improved and the light was converted to oil gas in January 1868.  The gas was made in a small gas works attached to the station; later gas was made from cannel coal.

Gas continued to be used until 1906 when the light source was converted to incandescent paraffin vapour using a 50mm diameter mantle.  The station was completely modernised in 1976 and the light converted from the paraffin to electric.

On 31st March 1994 the lighthouse was converted to automatic operation and the Lightkeepers were permanently withdrawn from the station.  The two former lightkeepers houses were sold into private ownership later in 1994.  That was a brief resume of the history of the lighthouses here at Wicklow.

Turning now to this octagonal tower which as you will recall dates from 1781, let me briefly explain the background to the relationship between Irish Lights and the Irish Landmark Trust.  In 1993, the Irish Landmark Trust, of whom you will hear more in a few minutes, expressed an interest in the octagonal tower considering it to be of architectural interest and a worthwhile building to rescue.  Following on from those initial discussions, the Irish Landmark Trust signed a 35 year lease agreement with Irish Lights in respect of this tower in May 1996.  The Trust have restored the tower with great sensitivity completing its work in March 1997.  They have since been successfully marketing this property as a short term holiday let.  Holiday letting generates income for the Trust, which is used to maintain the properties.  Following the success of this tower at Wicklow, Irish Lights have leased 5 other properties at three lighthouse stations to the Irish Landmark Trust.  Restoration work has been carried out on those properties and all are currently available to the holiday letting market.  Three further properties at two lighthouses are scheduled to be completed within the next 2 – 3 years.

At this stage, I would like to introduce Mary O’Brien, Chief Executive of the Irish Landmark Trust.  Mary will say a few words on the work of the Irish Landmark Trust and she will also explain the restoration work undertaken in the octagonal tower.  I hope you will enjoy your short visit to Wicklow Head this morning.

## Eoghan Lehane

Civil Engineering & Property Manager

Commissioners of Irish Lights

16 Lower Pembroke Street

Dublin 2

Ireland.

Tel:	+353 – 1 – 632 1990

Email:	e.lehane@cil.ie

COMMISSIONERS  OF  IRISH  LIGHTS

WICKLOW  HEAD  LIGHTHOUSE

52°57.9'  North

5°59.8'  West

## Aids to Navigation

Light:  Fl (3) W 15s.

Nominal Range:  23 nautical miles.

Height of Tower:  14 metres.

Height of light above MHWS:  37 metres.

Wicklow Head, 84 metres (275 feet) high, lies 3km south east of the town of Wicklow past the ruins of Maurice Fitzgerald’s Anglo-Norman Blackcastle.

Cill Mhantain or Mantan’s church is named after a disciple of Saint Patrick and according to the Annals of Clonmacnoise, Mhantain (the toothless) landed with Saint Patrick near Wicklow in 432 AD before heading north to Strangford Lough.  Unfortunately for Mhantain, he lost his front teeth by a blow of a stone from one of the Celtic pagans who had come down from the hills to oppose the landing of Saint Patrick.

Wicklow is derived from the Viking name Wykylo or Viking’s Loch.  The creek 4 km (2.5 miles) long is separated from the open sea by a long narrow grassy spit of low land known as the Murrow or Murragh.  The creek made an excellent harbour of refuge for the Norse sea-rovers and indeed, subsequent mariners.  The present harbour piers were not built until much later with a small local authority lighthouse on the east pier established in 1884.

Two lighthouses, one on Long Hill, the other on the saddle of the head, were built by the Revenue Commissioners to the design of John Trail their engineer, who previously had been involved with the Grand Canal Company between 1769 and 1777.  The two lights were established on 1st September 1781.  They not only marked the headland but prevented mariners from confusing Wicklow Head with Howth and Hook Head, both of which had single lights.  The two lights at Wicklow also gave a lead west-north-west between the south end of the India Bank and the north end of the Arklow Bank, and more locally through the Wicklow Swash to the anchorage off Wicklow tower or the coastal channel to Dublin.

Each octagonal stone tower supported an eight-sided lantern of which the five seaward sides were glazed with a number of ‘bulls-eye’ panes and a dome covered each lantern.  The light source in each lantern was twenty tallow candles at the focus of a large mirror reflector.

The rear tower is extant, minus its lantern but with a brick protecting dome which was added in 1866.  The tower is approximately 29 metre high to the balcony.  As no trace or drawings exist of the front tower on the headland saddle, one can only presume that it was similar to the rear tower, possibly not as high and definitely, according to a report dated March 1812, had an eight foot diameter lantern.  Again in 1816 another report stated “...and the second which is a smaller one in a proportionable degree”.

Soon after the Corporation for Preserving and Improving the Port of Dublin took over the lights from the Revenue Commissioners in 1810, the Wicklow Head lights were considered for rebuilding at a lower level due to the fact that the rear or upper light was liable to be obscured by fog; also both lights were in a very dilapidated condition.  The lanterns were rotten and rusty and the reflectors tarnished.  An attempt was made to improve the reflectors by cementing small pieces of looking glass in the large catoptric reflectors with six candles placed in their assumed focus.

Approval to build two new lighthouses was obtained from Trinity House and the Lord Lieutenant in 1816, and work commenced before the end of the year.  Mr George Halpin, the Board’s Inspector of Works, designed and supervised the building of the lighthouses which was carried out by the Board’s tradesmen.  Both towers were erected on the same bearing as the 1781 towers, with the new upper lighthouse close to the old front tower and the new front lighthouse tower down the cliff, 37 metres above high water level.

The new lights were fixed, each lantern housed fifteen Argand oil lamps and reflectors supplied by Messrs Greenside Company of Edinburgh and were established soon after 12th November 1818.  The 1781 front tower was completely demolished and at the same time the rear light was discontinued but the tower remained, forming a useful landmark by day.

The approximate overall heights of the two new towers were: upper (rear) 75 feet (22.8m) and lower (front) 45 feet (13.7m).  Both towers were painted white.

Soon after the new lights were established, the Board agreed with Inspector George Halpin’s report that the two existing keepers, Leonard Manley and George Wilkinson, be replaced as they were unqualified for any of the newly constructed lighthouses; they were also to surrender their dwellings.  Mr C. Dudgeon, the Wicklow Lighthouses’ Collector and Inspector should be informed that his services were unnecessary but should be paid to the end of the present quarter, December 1818.  All three men appealed on the grounds of long and faithful service.  The Board awarded the two keepers pensions of £15 per annum and Dudgeon received £50 in respect of his twenty years service.

Three years later, in 1821, the Revenue Commissioners, who from 1796 to 1810 had managed the lighthouses, thought they could re-instate their Preventive Water Guard along with a flag mast and take over the two ex-lightkeepers’ ‘cabins’ at the station.  The Revenue Commissioners were told that Regulations of the Service prevented the Board from complying with their request.  (Messrs Halpin, Bigger and Baker had noted in their report to the Board dated 21st September 1810 that the underpart of the large Wicklow Head Lighthouse was appropriated for the use of the officer who commanded the Signal Station.  When the guard was withdrawn is not known, probably soon after the Corporation took over).

On the night of 10th October 1836 lightning struck the old back tower and in the ensuing fire the lantern and all floors were completely gutted.  Mr Halpin stated in his report that as the tower formed a useful landmark by day, he recommended it should be re-roofed next Spring.  It is interesting to note that it was not until 1866 that the present brick dome was added.

On 30th June 1865 a new lightvessel, known as the Wicklow Swash, was established off the Head and the upper or rear light was discontinued.  This exercise was the result of one of the recommendations of the Committee, set up in 1863, to improve the lighting of the south east coast between Kish and Tuskar.  The vessel had a fixed red light.  Its life was comparatively short and was withdrawn on 10th October 1867 when the Codling and North Arklow lightvessels were established.

Coinciding with the discontinuance of the upper light in June 1865, the lower light was improved.  The 1818 lantern was replaced by a cast iron lantern supplied by Messrs J. Edmundson & Co., Dublin and the fixed catoptric apparatus was replaced by a Chance Brothers, Birmingham, first order dioptric lens with a revolving shade to give an occulting character of ten seconds flash every fifteen seconds.  The oil lamp was supplied by Messrs W. Wilkins, London, to the design of Captain Nesbit, Trinity House.

About this time, the Commissioners of Irish Lights were established in that name by the Dublin Port Act of 1867.  This Act separated the Corporation for Preserving the Port of Dublin into two authorities, namely, the Dublin Port and Docks Board, and the Commissioners of Irish Lights.

Following the success of Mr. J. R. Wigham's experiment with gas at the Baily Lighthouse in 1865, the light at Wicklow was converted to oil gas on 4th January 1868.  The gas was made in a small gas works attached to the station; later the gas was made from cannel coal.  The occulting character was effected by a gas valve being turned on for ten seconds and off for three.  In reality, the gas was not completely turned off, it was lowered to an almost invisible point before being raised for the ten second "flash".  If by chance the lowered flame did go out, a by-pass light re-ignited the main flame.  Altogether there were 108 jets each with 20 fish tail jets.  Thus it was possible to employ lights of five different powers.  The resultant flame produced by the jets was concentrated into a mica funnel set at the focal point of the lens.

Gas continued to be used until 21st August 1906 when the light source was converted to incandescent paraffin vapour using a 50mm diameter mantle.  The optic was also replaced by a Chance Brothers third order revolving apparatus driven by a David Brown clockwork rotation machine, giving three flashes every ten seconds.

The station became relieving on 1st October 1974.  It was then completely modernised and the light converted from the paraffin to electric on 31st March 1976.  Two months later, the Codling and Arklow lightvessels were withdrawn and replaced by Lanby buoys which were monitored by the Keepers in the Watch Room, built on top of the Keepers' quarters.  They are now monitored by remote link to the Lighthouse Depot in Dun Laoghaire.

A radiobeacon was established on 5th April 1978.  In more recent times utilisation of radio direction finders by mariners has been, to a great extent, superseded by more modern technology.  For this reason the Commissioners discontinued their Medium Frequency Radiobeacon service at Wicklow Head on 1st April 1992 and at all stations on the 1st February 1999.

On 31st March 1994 the lighthouse was converted to automatic operation and the keepers were withdrawn from the station.  The station is in the care of an Attendant and the aids to navigation are also monitored via a telemetry link from Irish Lights Dun Laoghaire.

Before concluding, it is interesting to note that the upper 1818 tower and what were the two keepers’ cottages were leased from 1891 to the Admiralty (Coast Guard); Board of Works who took over in 1922, one or two private lessees; and from 1935 until 1942 the Irish Youth Hostel Association.  On 1st May 1996 the Irish Landmark Trust leased the octagonal tower for a period of 35 years.  This tower is now being used as a holiday home.